## Data_summary
SN | Project | search_db | Project1 | Region | Type | Total PO Amt | Billed Till Date | Accrual | Total Revenue | Open AR | Open Billing | Billed YTD_FY25-26 | Current Month Billing | Project Duration | Billed | Billing Milestone | Project Dates | Resource | Milestone billing amount | Scope | Overall Progress | Weekly Plan | Technology / tools | Challenges / Risks | Update Date | Profit_YTD MIS | Profit_FY24-25_MIS | search_db1 | Project Manager / Lead
1 | INVEST INDIA | PMG INVEST INDIA | INVEST INDIA | North | Application Maintenance | 840.2445 | 587.4402 | 23 | 610.4402 | 110 | 252.8044 | 140.0408 | 23.3401 | 36 Months | 69.91% | Monthly | Start Date (PO) : 17-Jul-23 :: End Date (PO) : 16-Jul-26 | 14 | 23.34 L | Hiring of Professionals for -- Application Development and Maintenance – 36 months Front End and Back End developer – 8 Resources Full Stack developer, Solution Architect, QA Engineer, UI/UX designer, business analyst, QA automation tester, Project Manager – 1 resource each | Billing Done till Aug-25 Payment received till Jun-25 Released on production- 374 UAT- 2 Testing- 10 InProgress- 13 To-Do - 17 Designing- 3 Estimation- 10 | 1- Task deployed on 23/09 2- Task planned to deploy | NodeJS , HTML5/CSS , JS , React , Springboot Elastic, PostGreSQL , MySQL , MongoDB, Postman, API & SSO integration | One Resources Need to deploy | 2025-09-24 | 54.85% | 43.23% | PMG INVEST INDIA | Amit K
2 | SBM-U | SWACHH BHARAT MISSION - SBM URBAN | SWACHH BHARAT MISSION - SBM | North | Application Maintenance | 1305.45 | 717.0617 | 36 | 753.0617 | 92 | 588.3883 | 217.575 | 36.2625 | 36 Months | 54.93% | Monthly | Start Date (PO) : 10-Jan-24 :: End Date (PO) : 09-Jan-27 | 20 (7+13) | 36.26 L | Development, Maintenance and operations of an Integrated Portal for SBM used by the MoHUA Update and maintain the various modules and functionalities developed as a part of the “Integrated Swachhatam” portal update and maintain all mobile applications developed Resolve all the bugs, issues and queries raised for these developed functionalities | 20 resources on-boarded. (13 resources from GAIA – Tech Partner) Payment received till May’25. Invoicing done for Aug’25. 2 resources onboarded for SS. Hiring ongoing for 3 resources from GAIA. DWR mobile app: changes ongoing for dumpsite. New SBM Dashboard ver2.0 (Legacy waste & Toilets): testing ongoing New SSJ page created for City pairing on website. UWM Action Plan: additional points added from CPEEHO: Dev Ongoing API written for Prayas, under testing. GFC-I4 Indicator logic understanding and automation ongoing. Engineer App: Geo location enabled in iOS/Android. Implementation of Media Service in Java-Ongoing. Bulk upload parser under implementation. Website updates ongoing. Migration of SBMurban.org domain from Cloud Flare to Cloud Front. | Maintenance activities: Daily ULB support, Website changes ongoing. New SBM Dashboard 2.0 development: legacy waste & Toilets: testing ongoing. Updates in SSJ page. DWR Mobile App pilot planned in Oct’25. Enable DWR for Dumpsite. SS Handover with IPSOS ongoing. | Angular, AWS Cloud, mySQl, Posgresql, NodeJS, Java, MongoDB, RESTAPI, HTML, PHP, MicroService, Quicksight,CSS, Flutter | Major Challenges: 1. Need 3 developers (1 Angular + 1 NodeJS + 1 Power BI) from GAIA 2. DS has asked team whole team to work from SBM office. Majority of team members are working remotely. 3. No WiFi at New location | 2025-09-25 | 20.4% | 19% | SWACHH BHARAT MISSION - SBM URBAN | Anoop K
3 | ORGI | orgi OFFICE OF REGISTRAR GENERAL OF INDIA - CRS | OFFICE OF REGISTRAR GENERAL OF INDIA - CRS | North | Application Maintenance | 849.8214 | 402.0658 | 67 | 469.0658 | 33 | 447.7556 | 148.5513 | 33.611 | 2 Years | 47.31% | Monthly | Start Date (PO) : 02-Apr-24 :: End Date (PO) : 01-Apr-26 | 26 | 35.2 L | Maintenance, operations & enhancement of ORGI CRS Web and Mobile Application(s) including migration of legacy data from State CRS applications to ORGI CRS and vice-versa through APIs. Resources for 2 years as below – Data Analytics, Database Administrator, Mobile App. Developer Android, Mobile App. Developer iOS, System Admin, Team Lead/Technical Project Manager, Training and Change Management Engineer, UI / Web Designer - 1 resource each. API Developers, Quality Assurance/ Test Engineer, Senior Application Developers – 2 resource each Application Developers, Technical Support (helpdesk) – 6 resource each | 1. 26 Resource deployed. 2. Development of new Module is under process as per CRS requirement. 3. DB and System performance and monitoring continue above 99.6 % availability. 4. State onboard is on going. 5. Receive Data from Non CRS State through API. 6. AADHAR , TRANSLITRATION and Payment Integrations. | 1. June Payment under process from . 2. July Document approval pending from RGI. 3. August document verification under processing. 4. Deployment of GP Can extract Certificate, Application Flow Correction for Puducherry, Handling death events for where deceased’s permanent residence is outside India, Notification via SMS & Email for Contact Details Update on Registrar Profile and Including Date of reporting in Acknowledgement slip . 5. ORISSA DATA Mapping On Going. 6. Meeting with RGI is Scheduled on 26-Sep | Node JS, Android, iOS, ORACLE database , REST, API design, HTML, CSS, JavaScript, JSON, IIS/ Apache, Linux, Aadhaar Vault, NSDL PayGov, C-DAC | 1. Indore IMC Zonal register creation 2. Puducherry states will join CRS portal from 1st Oct with three regional Languages. 3. WSO2 to NAPIX Shifting. 4. Extension Approval Submitted. 5. Approval for Kalyan, Gaurang, and Roopali is pending. August attendance will be verified after approval. | 2025-09-25 | 22.12% | 11.94% | orgi OFFICE OF REGISTRAR GENERAL OF INDIA - CRS | Dhananjay J
4 | ECCS NEW | EXPRESS CARGO CLEARANCE SYSTEM – ECCS NEW 2.0 | EXPRESS CARGO CLEARANCE SYSTEM – ECCS 2.0 | West | Application Maintenance | 2413.026 | 399.2692 | 182 | 581.2693 | 471 | 2013.7567 | 399.2692 | 0 | 2 years (incl. 3 month HOTO) | 16.55% | Quarterly | Start Date (PO) : 26-Sep-24 :: End Date (PO) : 25-Sep-26 | 68 | 287.27 L | Application Support, Onsite support Helpdesk Operations and Maintenance Services and upkeep of the ECCS Application Manage and deliver current and proposed CRs Deployment of Project Management software tools as per RFP Technological Upgradation of ECCS application The vendor is responsible for ECCS application technological upgrade. Application Upgrade Version Upgrade Architecture Upgrade User Interface Upgrade | JF 20% Payment received. 1 out of 4 saddhit item released. The remaining tasks are in progress and planned for production deployment. All AMJ individual approvals received. | Provide different format of Attendance in Summary Sheet required by MA Team. Consolidated approvals proceeding. MIS resource closing. DBE interview proceeding. Getting July and Aug Attendance. | Java Struts, For upgrade - TBD | Productivity challenges observed among a few employees. Certain SLA parameters are challenging to achieve. Attendance marking on the CBIC portal for overlapping period of employee. RCA is in progress by WZU for full attendance marking on the CBIC portal by CMS for the past months.- Few verifications questions has given to study and answer. - July attendance approval raised by wzu. | 2025-09-25 | 37.26% | 33.03% | EXPRESS CARGO CLEARANCE SYSTEM – ECCS NEW 2.0 | Rahul S / Asmita S
5 | PFRDA | PENSION FUND REGULATORY AND DEVELOPMENT AUTHORITY - PFRDA | PENSION FUND REGULATORY AND DEVELOPMENT AUTHORITY - PFRDA | North | Software Development | 1265.6947 | 435.4656 | 0 | 435.4656 | 367 | 830.2291 | 0 | 0 | 1 yr Proj + 1 Yr Warr + 4 Yr AMC | 34.41% | 10% SRS ( 2m), 10% UAT( 7m), 10% VAPT/Audit ( 8m), 50% Implementation (9m), 10% training( 10m), 10% final Go-live ( 12m) for Solution cost of 622 L | Start Date (PO) : 18-Dec-23 :: End Date (PO) : 17-Dec-29 | 25 | As per achievment | Design, development, implementation and maintenance of PFRDA intranet portal(PINTRA) - internal digitalization (HRMS and finance) along with mobile app for HRMS Modules – HRMS, Finance, Admin, Legal, IT Management System 9 months Go-Live + 3 months Stabilisation + 1 Year Warranty + 4 Years AMC Payment Milestone : 10% SRS ( 2m), 10% UAT( 7m), 10% VAPT/Audit ( 8m), 50% Implementation (9m), 10% training( 10m), 10% final Go-live ( 12m) for Solution cost of 622 L Quarterly Payment for below; FMS during Warranty – 0.5 L / Qtr for 4 Qtr = 2 L MeitY empanelled GCC / VPC – 13.5 L/Qtr for 20 Qtr = 271 L Support Payment for Operations – 17.6 L/Qtr for 20 Qtr = 354 L CR – 17 L as & when required | Section 1 1. Print option to include the header of subject – List of Holidays observed during the calendar year ….. (Done) 2. Movement, sent to, sent from, purpose, status is not covered. (Done ) Note: For Movement -""Sent to"", ""Sent from"" should correctly shown on action perform) 3. Maker Checker to be covered (Done ) 4.On approval, calendar all over ERP to highlight RH, Public holidays, Saturday, Sundays in different colour. (On Dashboard Calender Description of holiday name is required when user click on particular date of Holiday)-Done 5.Leave rules/business logic should also consider the RH, Public holiday, Saturday, Sundays while calculating no. of days based on logics set.(Done) Section 2 1. Applying for multiple types of leave is not covered. Leave Type – Multi-selection of leave option as per business rules (CMS: New Feature) 2. Reason – Drop down to be available along with any other option. (CMS: Client already removed this requirement, now the client again wants this requirement) 3. Station leave period is different from leave applied period, therefore, after you want to apply for station leave, from and to date of station leave to be get captured. (CMS: Resolved) 4. Do you want to apply for station leave – ‘also’ after station leave word to be added (CMS: Not to Implemented, a separate leave type STNL is added instead). 5. Contact no. while of leave - Check box to select contact as available in office records / update different contact no. (CMS: Resolved) 6. Option to add multiple station leave to be available.(CMS: New Feature) 7. The slot is to be opened only upon selection of casual leave. Except for casual leave, no half day is allowed for any other type of leave. (CMS: Resolved) 8. After selection of from & to date and slot selection – no. of days leave applied to be viewed. (CMS: Resolved) 9. Related document – view option to be available . (CMS: As per Discussion – View Detail screen is already present) 10.Before submission, message pop up before final submission. (CMS: As per Discussion –Not to be Implement). 11. While selecting date from calendar RH, Public holidays, Saturday, Sundays are to be shown in different colour. (CMS: Provision is already implemented) 12. Leave rules/business logic should also consider the RH, Public holiday, Saturday, Sundays while calculating no. of days based on logics set. (CMS: Resolved) 13. On selection of from and to date- no. of days to get auto-calculated considering RH, Public holiday, Saturday, Sundays, and applicable business logics. (CMS: Resolved) 14. How to apply only for station leave is not clear. CMS: Leave Type for Station Leave is already implemented Notification on leave submission/ approval/ return to be shown under dashboard, e-mail, message is not covered. (CMS: New Feature, not feasible) 15. Applying for station leave only is not allowed in the given UAT. Error is shown. (CMS: Resolved) 16. In case of dual reporting, how leave to be get approved or to whom it will sent is not clear. Information of leave to be available with both the reporting officers. (CMS: Approval flow is already implemented; not feasible at this moment) 17. In case of reporting officer is on leave, pull option is available with officer to send leave to alternate reporting office / next higher authority by searching name of the officer and send option. (CMS: Approval flow is already implemented; not feasible at this moment) | Mobile Application – Apple iOS UAT observations of IT, Admin and Legal modules Go live compliance documentation in line with the RFP VAPT to be done - VAPT environment created & shared with AKS IT for further process. | Spring Boot, Odoo, React JS, Apache, PostgreSQL, Postman, Moodle, Figma, Ubuntu, AWS Cloud, Flutter, React, Node JS | ODOO resources for completion of pending tasks | 2025-09-18 |  |  | PENSION FUND REGULATORY AND DEVELOPMENT AUTHORITY - PFRDA | Dharmendra J
6 | DIC NHAI | DIGITAL INDIA CORPORATION - NATIONAL HIGHWAY AUTHORITY OF INDIA DIC NHAI | DIGITAL INDIA CORP - NATIONAL HIGHWAY AUTHORITY OF INDIA | North | Software Development | 2186.28 | 325.5 | 245 | 570.5 | 77 | 1860.78 | 325.5 | 162.75 | 3 Years | 14.89% | Track 1 (2m) - 10%, Track 2 (4m) – 20%, Track 3 (6m) – 20%, 8m – 50% | Start Date (PO) : 13-Nov-24 :: End Date (PO) : 12-Nov-27 | 32 | As per achievment, Phase 1 - 321 L | Developing and Maintaining a state-of-the-art Application to support transaction-based business processes covering entire lifecycle of National Highway projects of NHAI – Data Lake 2.0 upgradation. Payment Phase & milestone wise Track 1 (2m) - 10%, Track 2 (4m) – 20%, Track 3 (6m) – 20%, Track 4 (8m) – 50% Every phase of 6 months. Deployment of proposed 33 resources. (+5 in phase 2) | All Nine modules of Phase I done in UAT. Drone moved to Phase II Phase II requirement gathering done for BICRS, Road Closure, and Payments Development started on BICRS module. | Deployment of RSA, TM and BICRS on production. Start development of Road closure. Requirement gather for other modules of phase II | No-SQL, Ruby, Python, Java, HTML, CSS, JavaScript, Angular, React, GIS/ML, Cloud - TBD, Node JS, Rest API | Phase ll timelines are tight given the volume of work and current resources. | 2025-09-25 | 21.41% | 32.59% | DIGITAL INDIA CORPORATION - NATIONAL HIGHWAY AUTHORITY OF INDIA DIC NHAI | Mukul K / Agam V
7 | DAnFW | DEPARTMENT OF AGRICULTURE CORPORATION AND FARMER WELFARE DIVISION MINISTRY MAOFW DANFW DACFW dept of agri. | DEPT OF AGRICULTURE CORP & FARMER WELFARE | North | Application Maintenance | 1606.08 | 497.1459 | 68 | 565.1459 | 99 | 1108.9341 | 385.6203 | 67.878 | 2 Years | 30.95% | Monthly | Start Date (PO) : 05-Dec-24 :: End Date (PO) : 04-Dec-26 | 52+2 | 67.88 L | Deployment of technical resources for application development, customization and maintenance for ‘digital agriculture division, DA&FW’ Deployment of required 34 resources. 1 resource each – Team Lead, Sr Mobile Developer, tester, BA, content management expert. 2 resource each – Full stack/Sr Developer, UI/UX, API developer, mobile developer, dashboard expert, e-office support. 3 resource each – Sr Front end developer, VC support 5 resource – Full stack developer (>6 to <10 yrs.) 6 resource – Full stack developer (>3 to <6 yrs.) Deployment of 16 resources on need basis. | 1] Krishi MApper – Telangana State API for NMEO-OP : meeting schedule Optimizing current GIS Dashboard KM Dashboard new layout is in progress NBM/PKVY/oil seed assets : scheme to onboard by 30th. 2] Natural Farming : Fixing users highlighted issue 3] NFSM – Agristack data pushing on live(hold as discussed in meeting) . Fetch data directly from Agristack API 4] NMEO-OP – VGP module is in Progress 5] NMEO-OS- Working on changes request 6] MIDH-APP – Added 8 new components in mobile app online mode/Offline mode and deployed on play store 7] Krishi Unnati – Master data/Annual Action plan/budget head wise data is done and showed to client. History version is going. Discussion for MIS report scheduled. | 1] NBM/PKVY/oil seed assets : scheme to onboard by 30th. 2] PDMC/AMI/other API : push data on user management/GIS dashboard/survey data count 3] AIKOSH API : development of metadata API for all existing scheme. 4] DCS dashboard : Data duplicity check with 3rd party and show data over dashboard | C#, ASP.NET, MVC, .NET Core, Visual Studio, HTML5, CSS3, RESTful API, MERN, flutter, react Native, MS SQL, e-Office | Database Developer require for SP, DB, API optimization due to heavy load of data. | 2025-09-25 | 11% | 11% | DEPARTMENT OF AGRICULTURE CORPORATION AND FARMER WELFARE DIVISION MINISTRY MAOFW DANFW DACFW dept of agri. | Sourav M / Ravi R
8 | GWALIOR SC ICCC | GWALIOR SC ICCC | GWALIOR SC ICCC | West | Smart City | 1372.5806 | 430.5498 | 46 | 476.5498 | 204 | 942.0308 | 74.7324 | 33.4494 | 62 month (incl. 2 mnth HOTO) | 31.37% | FMS – 11 L + Taxes (monthly billing) O&M – 13 L + Taxes (quarterly billing) Audit – 8 L + Taxes (yearly billing for 1st Year) Upgradation – 324 L + Taxes (60% - 194 L) | Start Date (PO) : 30-Aug-24 :: End Date (PO) : 31-Oct-29 | 32 | As per milestone | ICCC & DC upgradation with 5 years comprehensive AMC – 60% on SITC & 2% every Quarter with O&M payment CAMC of existing IT & non-IT infra - quarterly payment Manpower services: 39+1(non-billable) – monthly payment ICCC certifications – Yearly payment Provision – as & when required. | Q3 Billing done and payment in progress. ISO Work in progress Minimum wages letter submit to operators with clarification. Remaining manpower approval letter submit to client for approval as per BOQ. | Q3 Payment file reach to accounts for payment ISO audit documents reviewed by clients. AMCs pending for server, tapes, switches and San switch from Management and Purchase team. | NA | ISO Audit related discussion required sales team to client. AMCs required IT , this is critical 1st Floor 20no's AC AMC required ASAP. | 2025-09-25 | 19.54% | 11.44% | GWALIOR SC ICCC | Sachin S
9 | Kanpur SC O&M | Kanpur SC O&M tech mahindra TECHM | Kanpur SC O&M | North | Smart City | 5337.5 | 3431.25 | 635 | 4066.25 | 916 | 1906.25 | 762.5 | 0 | 42 month | 64.29% | Quarterly | Start Date (PO) : 01-Jan-23 :: End Date (PO) : 25-Jun-26 | 46 | 381 L | O&M support, AMC of all BOQ. Maintenance of Hardware, Network, Software, ICT Infrastructure, L1 , L2, L3 & OEM Support of all field solutions, DC & DR and applications for 42 months ( 50 junctions ) BG for 762 L to be submitted, advance payment of 2 Qtrs will be released after signing SOW. BG would be returned back to CMS after 4 Qtrs. PBG of 3% of balance of TCV (137 L) to be submitted at end of Qtr 4. | Jan 23 to Mar 25 (Total 9 quarters payment released-75%). 24 July meeting scheduled with commissioner to discuss issues related to ICCC critical issues & withold payment — KSCL will not pay to TechM (re-imbursement) & has to be paid by TechM to CMS. Billing done for OND24 & JFM25 Qtr. Neat-Park application demonstration to client is carried out on 23rd Oct 2024; Client has suggested few points, Team has incorporated the same - Payment integration is in progress (Bank details awaited from client - will share after VAPT) — VAPT completed & feedback points also closed on 28-Aug-25. EMS OEM onboarding done - OEM Team repairing work in progress. Collected ~ 632 L till JFM-25. | ATCS work scope of fully operationalising 23 locations in progress Consolidation of inventory for metro route chunni ganj to Naya ganj for sharing it with Metro vendor for imdeninification of lost or damaged material VMSB to be made functional by repairing card SMPS or fcr cable damages Reimbursement of recurring charges from TechM. Release of 25% retention/withheld amount — In progress. | NA | Many software/application licenses have expired with OEM and needs renewal | 2025-09-25 | 25% | 51.23% | Kanpur SC O&M tech mahindra TECHM | Saleel H
10 | NMPT | NEW MANGALORE PORT TRUST - NMPT | NEW MANGALORE PORT TRUST - NMPT | South | CRP | 680.6929 | 225.4923 | 22 | 247.4923 | 50 | 455.2006 | 6.3876 | -14.3592 | 5 years | 33.13% | Monthly | Start Date (PO) : 01-Jul-24 :: End Date (PO) : 01-Jul-29 | 15 | 7.3 L | Operation and Comprehensive annual Maintenance Contract (CAMC) of the RFID System for a Period of 5 years at NMPA. FMS – 12 data entry operators, 2 Technician, 1 Service Engineer Replacement of existing Infrastructure in 1st year. – 197 L (inc. KK & Cruise gate augmentation). Payment within 15 days after SITC of replacement. Integration with existing system. | 1. Hardware installation is in progress at KK gate and Cruise gate 2. March\April 2025 CAMC bill in progress by NMPA finance dept. 3. Turnstile should be rectified, awaiting inputs from purchase team to issue PO to turnstile OEM. 4. Material procurement is in progress for Visual alarm system at NMPA. | 1. Completing installation of KK gate cruise gate. 2. Handover the site to NMPA | NA | Turnstile vendor PO not yet released | 2025-09-25 | -23.92% | 12.04% | NEW MANGALORE PORT TRUST - NMPT | Prashant P
11 | Vadodara Traffic | VADODARA VMC TRAFFIC | VADODARA VMC TRAFFIC | West | Smart City | 1045.7627 | 709.4025 | 0 | 709.4025 | 0 | 336.3602 | -0.5941 | 0 | SITC 4 Mths & O&M - 5 Yrs | 67.84% | After SITC | Start Date (PO) : 26-Feb-24 :: End Date (PO) : 25-Jun-29 | shared resources | full | Design, supply, Erection testing & commissioning of traffic signal at various 28 junction. Upgradation of old traffic signal at 44 Junction. Integration with existing system. 5 year comprehensive maintenance service. Payment 100% after successful installation. | O & M work is going on. 302 new traffic light under procurement. | O & M activity | NA | 302 light deliveries pending. | 2025-09-26 |  | 18% | VADODARA VMC TRAFFIC | Sachin R
12 | VADODARA ICCC | VADODARA ICCC vadodara | VADODARA ICCC | West | Smart City | 2019.8763 | 331.9972 | 0 | 331.9972 | 0 | 1687.8792 | 171.1604 | 0 | 5 years | 16.44% | Quarterly | Start Date (PO) : 01-Aug-24 :: End Date (PO) : 31-Jul-29 | 17 | 100.99 L | O&M support, AMC of all BOQ. Maintenance of Hardware, Network, Software, ICT Infrastructure, L1 , L2, L3 & OEM Support of all field solutions, DC & DR and applications for 60 months Deployment of manpower : Project Manager (1), Technical Expert (4) [Network and Security, Video management, server-storage, CCC software], Electrician (4), Field staff (8) PBG of 3% | O & M continue in second year first quarter | O & M activity. All Projects Inclusive : ( ICCC , C1 ,C2 , VMC-Amrut ,VMC-P4 , VMC-CCTV ) All sever project are Under O & M First year Fourt quarter invoice we will submit this week --- ICCC Last Two quarter invoice are under process --- ICCC 302 Traffic light under procurement --- VMC ATCS C1 & C2 last quarter o & m invoice under process | NA | 20 no CDT and 5 no of DC controller spare material procurement pending since long time VMD application testing done but controller replacement activity pending. New controller under procurement --- ICCC 11 no of VMD LED tile have issue. Need to purchase new module - ICCC 22 no of UCON 10 controller we needs to replace. - ICCC 300 faulty module given to OEM for replace material --- VMC-P4 LED Two VMD module need under procurement- Gandhinagar 40 no location battery stolen. Insurance under process 17 no ups under repairing | 2025-09-26 | 21.71% | 20.46% | VADODARA ICCC vadodara | Sachin R
13 | ISCDL | INDORE SMART CITY ISCDL | INDORE SMART CITY | West | Smart City | 2903.0413 | 1722.0306 | 0 | 1722.0306 | 977 | 1181.0107 | 54.8212 | 0 | SITC – 9 M, O&M – 5 Yr | 59.32% | Quarterly | Start Date (PO) : 01-Nov-22 :: End Date (PO) : 31-Aug-29 | 6 | 43.3 L + Taxes (O&M) | Implementation of (ITMS) for 50 Junctions with Centralised Monitoring + 50 additional services Payment Milestone wise 5% Inception Report, 10% requirement Study, 30% material delivery & commissioning of 1 corridor ( 15 Junctions ) , 30% remaining delivery ( 35 junctions + 20 SVD + 20 ATCC and 10 TVD ) & commissioning, 25% Go Live. O & M : 5 Years CAPEX ~20.37 Cr & OPEX ~ 8.66 Cr | 1. Hold 11 ATCS and 9 ITMS junction work letter received. 2. Hold 3 TVDS, 3 SVDS, 19 PTZ location letter received. 3. Hold junction CAPEX cost approval and Billing mail received. 4. Submitted invoices for completed work including other recurring cost are under verification by CDO sir and ISCDL team. As per ISCDL CEO Sir confirmation, partial payment of 50 Lakh will be released by upcoming week. 5. Dt:- 26-09-2025, Note sheet will be reached at CEO sir table for signing. | 1. New junction work of one no. 3 Arm ATCS-ITMS approval will be received from ISCDL. 4. As per CDO sir, Go-Live note sheet are preparing and will be released in upcoming week. | NA | 1. Work approval required from HO for the execution of ISCDL letter for 11 ATCS junction, 9 ITMS junctions, 3 TVDS and 3 SVDS. 2. Material approval including dispatching required as per site consumption report. | 2025-09-26 | -5.274% | -20.41% | INDORE SMART CITY ISCDL | Akash K
14 | IREL | INDIAN RARE EARTHS LIMITED - IREL | INDIAN RARE EARTHS LIMITED - IREL | West | Software Development | 1047.3631 | 162.9668 | 0 | 162.9668 | 115 | 884.3963 | 0 | 0 | SITC – 12 Months , O&M - 4 Yrs | 15.56% | Milestonewise | Start Date (PO) : 29-Oct-18 :: End Date (PO) : 30-Sep-25 | 23 | As per Achievement | Development of Integrated ERP System (IITS) (326 L) FMS including support & maintenance (147 L) Cloud Services (574 L) Change Request (63 K) | Finance: 1.Internal Management Reporting 2.Cross-Functional support in HRMS and Material 3.Bug fixing in progress 4.Error identification due to database updation in MM HRMS: 1. Verified and checked data for issues raised during the 3rd September demo, including: · Income tax calculation · Perquisite tax calculation for various perquisite values · View break-up functionality · Raising tickets and discussing solutions with developers 2. Met with the IREL HR team at HO Office and discussed: · Attendance report issues (fixed and moved into production) · Workflow-related issues · Attendance data of retired employees and missing date attendance · Shared resolutions with their HR team - Additionally, based on the points shared by Anil with Jena Sir: · Held discussions to understand the issues in detail · Suggested possible resolutions · Shared updates internally to ensure appropriate action is taken to meet expectations | Finance: 1.Operational Modules optimization 2.Response and bug fixing of the Chavara Unit Email HRMS: 1. Demo with Jena Sir & Jyoti · Provide a demo on the points raised in the previous demo · Execute payroll runs for April, May, and June with updated logic 2. Ongoing Client Support & Coordination · Continue addressing daily payroll-related queries · Provide support for payroll operations · Assist clients in streamlining payroll processes to improve efficiency | Core Java, BIRD tool, postgre, ESDS cloud | Payment release | 2025-09-15 |  | -955.1% | INDIAN RARE EARTHS LIMITED - IREL | Priya R
15 | Guwahati SC | Guwahati SC Honeywell Automation India Limited | Guwahati SC | East | Smart City | 669.1843 | 583.8884 | 0 | 583.8884 | 325 | 85.2959 | 268.734 | 6.223 | 1 Year + O&M | 87.25% | 10% of capex - Submission of Survey report, built report, project deployment plan. 50% - supply of material on pro-rata basis 15% - installation of material on pro-rata basis 15% - commissioning on pro-rata basis 5% - Go-live on pro-rata basis for individual system 5% - Overall Go-live of complete project. | Start Date (PO) : 10-Feb-25 :: End Date (PO) : 09-Feb-26 | 2 | As per Achievement | SITC for --. 1] 20 ECB. 2] 20 PA. 3] 10 ENV SENSOR. 4] 10 VMD. 5] 1 GIS Software. -- 5 years O&M after Go-live for supplied BOQ. | 1] EVS- 10/10 EVS poles installed. Equipment installation pending due to power and network not available from Honeywell. 2] 6/10 VMD pole foundations done. Poles installation pending due to poles are not delivered till date. Rest foundation will be started after Durga Puja. 3] PA installation pending due to power and network not available from Honeywell. 4] ECB enclosure delivered at site on 23/09/25. Works will be started after Durga Puja. 5] GIS testing server is working. Main server still not provided by Honeywell. | For this week upto 21/10/25 works has been suspended by GSCL/ Nagarnigam. | NA | 1] VMD poles delivery issues. 2] Vendor cable laying order still not done. 3] Approved VMD controller still not sell delivered. 4] Accessories still not delivered. | 2025-09-25 | 36.66% | 20% | Guwahati SC Honeywell Automation India Limited | Arindam R
16 | MCS - L&T | Mumbai city surveillance larsen and toubro mcs | Mumbai City Surveillance | West | Smart City | 437.1641 | 433.0839 | 73 | 506.0839 | 257 | 4.0802 | 433.0839 | 72.0592 | 6 months | 99.07% | Monthly | Start Date (PO) : 01-Mar-25 :: End Date (PO) : 31-Aug-25 | 223 | 72.86 L | Viewing Manpower in 4 shifts including backup to cover 203 shifts daily. | MCS Project Updates 1) August-2025 month invoice has been submitted to Customer 2) Q32 Quarterly Report has been published and submitted 3) Doing follow-up with L&T for Next work Order | 1) Interview planned for 10 Candidates 2) User ID deletion from Customer Active Directory for resigned employees 3) Client and Operators List for Diwali Gift 4) Salary Attendance and Salary Sheet preparation | NA | 1) Awaiting for Work Order for MCS Project 2) New Recruitment of CCTV Viewing Officers 3) AR Collection for due Invoices | 2025-09-25 | 61.44% |  | Mumbai city surveillance larsen and toubro mcs | Jaywant P
17 | JNPA | Jawaharlal Nehru Port Authority JNPA jnpt | Jawaharlal Nehru Port Authority | West | EMS | 171.3136 | 155.5 | 0 | 155.5 | 0 | 15.8136 | 155.5 | 155.5 | 6 months + 5 Yr CAMC | 90.77% | Product Cost Payable on Product Delivery - 70% ICT Charges - 30% | Start Date (PO) : 07-Apr-25 :: End Date (PO) : 04-Oct-25 | 2 | 131.78 L | Design, Supply, Installation, Testing and Commissioning of web based enterprise energy and utility Management system with five years of Comprehensive Annual Maintenance Contract (CAMC) a) Complete built in energy monitoring system including power distribution monitoring of electrical & utility energy & consumption monitoring viz boundary level, process level and specific identified key areas. b) Demand management system that covers demand forecasting, scheduling and deviation monitoring w.r.t the schedule drawl c) Energy billing system that coverers consumer’s energy monitoring and billing ->>Functional Requirements/ Deliverables : DATA ACQUISITION SYSTEM // DATA MANAGEMENT SYSTEM // DEMAND FORECASTING MODULE // Deviation Settlement Mechanism Module //Demand Management Module // Utility Billing Module – Electricity, Water & Rental ->>Infrastructure Requirements: Server // Cloud Service (IaaS) // OS // DB // Networking | Primary & Backup Servers – Fully configured, tested, and installed. Ready for operation from 15-09-2025. Substations 1, 2 & 3 (MFM Meters) – Network setup completed. Awaiting switch rack installation by JNPA to enable data communication. ABT Meters – Installed and panel placed. Awaiting base installation, MSETCL testing, and switch installation for data connectivity. RMU Panel Communication – Survey and planning complete. Awaiting JNPA support for switch and OFC connectivity. Work can begin on RMUs currently offline. Water Flow Meters – 62 delivered, 3 installed. Awaiting infra readiness (valves, ducts, etc.) from Water Dept. for ~30 more installations. Larger meter installation delayed due to location finalization. | Software integration and deployment to client side | PostgreSQL, DLMS, MODBUS, GPRS, Python, DotNet MVC | Network Delays: Delay in switch installation and OFC connectivity by JNPA is holding up data retrieval across substations, ABT meters, and RMUs. Infrastructure Readiness: Water meter installations delayed due to pending civil and plumbing works (valves, ducts, power) from Water Dept. Coordination with Multiple Teams: Dependencies on JNPA Network, Water, and SCADA teams are causing bottlenecks in parallel progress. SCADA Integration Uncertainty: Lack of API or clear approval for EMS data retrieval via SCADA is stalling server-side integration. | 2025-09-25 |  |  | Jawaharlal Nehru Port Authority JNPA jnpt | Brayan F
18 | DIC ROB | DIGITAL INDIA CORP -PRD RAILWAY & ROB GIRDER INSPECTION PORTAL DIGITAL INDIA CORP -PRD RAILWAY & ROB GIRDER INSPECTION PORTAL DIC ROB | DIGITAL INDIA CORP - PRD RAILWAY & ROB GIRDER INSPECTION PORTAL | North | Software Development | 111.36 | 11.136 | 0 | 11.136 | 0 | 100.224 | 11.136 | 11.136 | 4 months + O&M | 10% | Track 1 - 10%, Track 2 – 20%, Track 3 – 20%, 8m – 50% | Start Date (PO) : 09-Jun-25 :: End Date (PO) : 08-Oct-25 | 12 | As per achievment. | Developing and Maintaining a state-of-the-art Application to used for handling the process related to constructing a railway girder over the roads/highways including various stages of requests, inspection and approval process involving different stakeholders/users. Need to automate & manage the process through web-based portal which is currently handled manually/paper-based. In Phase -1, The process related to Quality Assurance Plan (QAP) and Welding Procedure Specification Sheet (WPSS) will be automated. In Phase-2, rest of the processes to be automated. Payment Phase & milestone wise Track 1 - 10%, Track 2 – 20%, Track 3 – 20%, Track 4 – 50% Deployment of proposed resources for total 80 Man-months. | Module End Date Work Status Environment Authentication 4-July Done Production Landing Page 24-June Done Production Agency Selection 4-July Done Production View Girder Assign. 14-July Done Production WPSS & QAP Submission 19-June Done Production Approver 10-July Done Production Module Integration 29-June Done Production Inter Service Communication 29-June Done Production View Download GAD 20-June Done Production Add New Girder & Contractor 02-Aug Done Production Data Migration 28-June Done Production Agency Selection Module 30-July 29-Aug Done GAD Management Module 30-July 11-Aug Done Stake Holder & Employee Onboarding 12-Aug 8-Sep Done | Girder Fabrication & Raw Material Approval Process Email Integration Dashboard & Listing Management WPQR Preparation & Submission (Welding Procedure Qualification Record) | JAVA 17, Springboot, PostgreSql, React, AWS Cloud, Microservices, NodeJS, Postman, Apache Tomcat webserver, SSL, Oauth, AWS ECS | Frequently requirements changes from clients | 2025-09-17 |  |  | DIGITAL INDIA CORP -PRD RAILWAY & ROB GIRDER INSPECTION PORTAL DIGITAL INDIA CORP -PRD RAILWAY & ROB GIRDER INSPECTION PORTAL DIC ROB | Dharmendra J
19 | DIC NOC | DIC NOC | DIGITAL INDIA CORP - NOC | North | Software Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA | Start Date (PO) : 03-Jul-25 :: End Date (PO) : Order to log | 11 | NA | Development, deployment, and support of NOC Portal with modules for Login, User Registration, Application Submission, and Approval workflows. Implementation of Registration & Validation including Mobile OTP, GST validation, Aadhaar integration, and User Authorization. Enable Application Submission with GIS data pickup, document upload, affidavit submission, e-sign, payment gateway, and Q&A module. Workflow automation for Right of Way (ROW) applications with end-to-end submission tracking. | Total 9 modules (functionalities to be developed in this project. Completed - 4 In progress - 3 Pending (dependencies from Client) - 2 -> Module-wise Status with remarks as below; 1] UIDAI Aadhaar Integration - Pending -Awaiting initiation and final approvals. 2] CDAC E-Sign Integration - Completed - Fully integrated and tested. 3] Bharatkosh Payment Integration - Completed - Live and functional. 4] GIS Data Cleaning - In Progress - Data refinement activities underway. 5] GIS Data (Geo Server Setup) - Pending - Geo Server establishment blocked due to Docker image support issue; Shridhar is investigating. MoRTH confirmation is still awaited. 6] PA/CA/AE/IE User Data Cleaning - In Progress - User data validation and cleaning ongoing. 7] Amenity Listing - Completed - Finalized and ready for use. 8] Utility Listing -In Progress - Listing and validation activities ongoing. 9] Compliance Questions - Completed - Reviewed and approved. | 1] Work Order / LOI to be received. 2] Expedite resolution of Geo Server/Docker issue. 3] Obtain MoRTH confirmation for GIS data provisioning. 4] Initiate UIDAI Aadhaar integration post prerequisites. | 0 | ● GIS Data / Geo Server: Docker image issue hindering setup; pending MoRTH confirmation. ● UIDAI Aadhaar Integration: Implementation to begin after receiving required approvals and environment setup. ● Template creation for Provisional License and Final License. | 2025-09-19 |  |  | DIC NOC | Pradeep N
20 | NeGD ITPO | NATIONAL E-GOVERNANCE DIV - ITPO BHARAT MANDAPAM NATIONAL E-GOVERNANCE DIV - ITPO BHARAT MANDAPAM NeGD ITPO | NATIONAL E-GOVERNANCE DIVISION - ITPO BHARAT MANDAPAM | North | Application Maintenance | 509.88 | 0 | 0 | 0 | 0 | 509.88 | 0 | 0 | 2 Years & extendable for 1 yr | 0% | Monthly | Start Date (PO) : 25-Aug-25 :: End Date (PO) : 24-Aug-27 | 4 | 21.25 L | Hiring of 14 Professionals to -- Handle the software project development, support & rollout services of DIC-NeGD projects. Primarily the services would range from core project development, implementation to management support in carrying out regular operational activities on a day-to-day basis – For 24 months extendable upto 1 Yr. Front End and Back End developer – 8 Resources (Including 1 senior developer each) Mobile App Developer – 2 resources Quality Analyst, DevOps, Project Manager cum Business Analyst, Data Entry Analyst (Platform Management) - 1 resource each | ITPO new website development is in progress. We have been developed 11 pages till date along with mobile resposiveness. Accessibility feature on the website has been developed. For UAT purpose we have been deployed on Staging environment. The development of the new ITPO website is currently underway. We have developed 11 static pages so far, ensuring mobile responsiveness across all pages. Additionally, the website now includes an accessibility feature. For UAT, the site has been deployed to the Staging environment. | Following pages are planned to develop by next week- - Events (5 pages) - Visitors (3 Pages) - Explore Venues (2 pages) - Financial Results (2 Pages) - Activity & Services - Brouchures - Career at ITPO - Admin Panel | 0 | - One of our team members, Bhawesh Bhanu, is currently hospitalized. NeGD wants to ensure that there is no disruption in deliveries and that Bhawesh can actively engage in the upcoming KT sessions with the existing vendor. - NeGD has raised concerns about potential billing issues due to this situation. - NeGD has requested that if Bhawesh requires additional time for recovery, CMS Computers should deploy a senior backend resource (12-13 Years experience) with expertise in Node.js (Nest.js framework) to ensure continuity. | 2025-09-24 |  |  | NATIONAL E-GOVERNANCE DIV - ITPO BHARAT MANDAPAM NATIONAL E-GOVERNANCE DIV - ITPO BHARAT MANDAPAM NeGD ITPO | Raghavendra P
21 | MMRDA BTRS | MMRDA - BALASAHEB THAKRE RASHTRIYA SMARAK MMRDA - BALASAHEB THAKRE RASHTRIYA SMARAK MMRDA BTRS | MMRDA - BALASAHEB THAKRE RASHTRIYA SMARAK | West |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 months | 0% | 0 | Start Date (PO) : Yet to log Order :: End Date (PO) : . | NA | 0 L | EPC providing immersive experience in Gallery and Museum design with fit out and SITC of end-to-end solutions of technologies including existing systems, MEPF and O&M for 1 Year CMS Scope ( As Partner to EPC Contractor) SITC of BLE5 MESH NETWORK VISITOR MANGEMENT SITC of ICCC PLATFORM WITH LIDAR AND BI TOOLS SITC of VIDEO WALL & ASSOCIATED CONTROLLERS, CABLES & ACCESSORIES SITC of COMMAND & CONTROL ROOM INCLUDING CIVIL, INTERIORS, MEP SERVICES SITC of NETWORK, SECURITY MONITORING AND MANAGEMENT SITC of SERVERS , DESKTOPS AND ASSOCIATED INFRASTRUCTURE | We have still not received the order and SO is not generated, as per sales - Mr. Parag the final signature is awaited from customer side. | Once the Order is generated in our system we will ask Purchase to start taking the quotes and do negotiations along with Meeting with All identified vendors as per scope at site. | NA | Crisp delivery timeliness and multiple vendors to deliver the entire solution makes it complex and timely follow-up and push is needed. | 2025-09-25 |  |  | MMRDA - BALASAHEB THAKRE RASHTRIYA SMARAK MMRDA - BALASAHEB THAKRE RASHTRIYA SMARAK MMRDA BTRS | Vinod S