## Data_summary
SN | Project | Region | Type | Total PO Amt | Billed Till Date | Accrual | Total Revenue | Open AR | Open Billing | Billed YTD_FY25-26 | Current Month Billing | Project Duration | Billed | Billing Milestone | Project Dates | Resource | Milestone billing amount | Scope | Overall Progress | Weekly Plan | Technology / tools | Challenges / Risks | Update Date | Profit_YTD MIS | Profit_FY24-25_MIS
1 | INVEST INDIA | North | Application Maintenance | 840.2445 | 564.1 | 23 | 587.1 | 83 | 276.1445 | 116.7006 | 23.3401 | 36 Months | 67.14% | Monthly | Start Date (PO) : 17-Jul-23 :: End Date (PO) : 16-Jul-26 | 15 | 23.34 L | Hiring of Professionals for -- Application Development and Maintenance – 36 months Front End and Back End developer – 8 Resources Full Stack developer, Solution Architect, QA Engineer, UI/UX designer, business analyst, QA automation tester, Project Manager – 1 resource each | Monthly billing from July-23 to Jun-25 done. Application maintenance and regular CR deployment. 339 tasks out of 376 tasks are in production as on date Pragati meetings module is developed by CMS. These meetings are being chaired by Prime Minister of India. AWS Optimization has been done on all PMG environments as instructed by PMG team // Security Audit was done & agency has raised total 26 points out of which there are High Priority: 6 Tasks , 5 tasks are currently in progress. 1 task is pending client approval before initiation. -- meeting was scheduled for further discussion with client on 26 Jun & only 3 high priority points to be taken up. Already included in task list & are in progress. | Maintenance activities Deployment of 1 task -- on UAT 10 Tasks In progress. (+ 7 Tasks in QA Testing, +4 in designing, +9 under estimation & + 6 Tasks in to do) Due payment collection. (Mar to Jun 25) Replacement of Bimal Kalsa on priority (LWD 31 Jul 25- extended her for third time) | NodeJS , HTML5/CSS , JS , React , Springboot Elastic, PostGreSQL , MySQL , MongoDB, Postman, API & SSO integration | Replacement of Bimal Kalsa (Backend+Elastic Developer) - As per rfp terms we need to provide replacement with overlapping period of 30 days, if not then penalty equivalent to monthly amt of resource will be deducted. | 2025-07-24 | 47.86% | 43.23%
2 | SBM-U | North | Application Maintenance | 1305.45 | 680.7992 | 36 | 716.7992 | 92 | 624.6508 | 181.3125 | 36.2625 | 36 Months | 52.15% | Monthly | Start Date (PO) : 10-Jan-24 :: End Date (PO) : 09-Jan-27 | 7+13 (GAIA) | 36.26 L | Development, Maintenance and operations of an Integrated Portal for SBM used by the MoHUA Update and maintain the various modules and functionalities developed as a part of the “Integrated Swachhatam” portal update and maintain all mobile applications developed Resolve all the bugs, issues and queries raised for these developed functionalities | 20 resources on-boarded. (13 resources from GAIA – Tech Partner) Payment received till Apr’25. Invoicing done Jun’25. Daily Waste reporting mobile app development & testing done, bugs/feedback changes in progress. Campaign ‘SABB 2.0’ is Live. UWM Dashboard development done - addition of FSTP plant & SOAK on ULB login in progress. EOI Form testing complete & ready for production. DR Activity-Plan received from Hitachi. -- on hold as of now. | Maintenance activities: Daily ULB support, Website changes ongoing. Support to GFC & ODF-Field Assessment ongoing. Issue Resolution. Dashboard revamp in portal. Domain sbmurban.org to be renewed Mobile App to be developed for Daily data entry at plan level. New SBM Dashboard- Legacy waste section – data verification ongoing. DR activity-- on hold | Angular, AWS Cloud, mySQl, Posgresql, NodeJS, Java, MongoDB, RESTAPI, HTML, PHP, MicroService, Quicksight,CSS, Flutter | 0 | 2025-07-25 | 19% | 19%
3 | ORGI | North | Application Maintenance | 849.8214 | 339.0493 | 65 | 404.0493 | 38 | 510.7721 | 85.5348 | 0 | 2 Years | 39.9% | Monthly | Start Date (PO) : 02-Apr-24 :: End Date (PO) : 01-Apr-26 | 26 + 1 | 35.2 L | Maintenance, operations & enhancement of ORGI CRS Web and Mobile Application(s) including migration of legacy data from State CRS applications to ORGI CRS and vice-versa through APIs. Resources for 2 years as below – Data Analytics, Database Administrator, Mobile App. Developer Android, Mobile App. Developer iOS, System Admin, Team Lead/Technical Project Manager, Training and Change Management Engineer, UI / Web Designer - 1 resource each. API Developers, Quality Assurance/ Test Engineer, Senior Application Developers – 2 resource each Application Developers, Technical Support (helpdesk) – 6 resource each | Kick-off meeting with Customer done. Infra provided to resources by ORGI. Shadow & reverse Shadow phase completed. Independent development – Started & In Progress KT Activity – Completed Handover from HPE current SI: Completed Billing done from Apr-24 till May-25 ( New rates applicable from 2nd April 25) Received 37 L payment on 22-Jul-25. (cleared till Apr25) Daily Birth/Death count monitoring report - automation done Addition of Download link for the android app on communication email for RE/SR done Provision to authenticate the Aadhaar number for RE/SR done iOS App Live in App Store Correction in Adoption Case done Bihar Jurisdiction splitting done -- data shifting in progress. provision made for General Public -- can now download birth / death certificate for self & family (adhar authenticated) | 4 states will join CRS portal (all certificates will be issued from CRS) -- Gujarat, Pondicherry, Telangana & Delhi. Gujarat onboarding to be completed by 15th Aug. registrar payment reconciliation report work in progress. Audit log - for cyber forensics in case of fraudulent certificate generation. eSign on Android App Billing for Jun-25 after client returns & approves attendance. Indore IMC Zonal registar creation. Replacement of Vikas Kohli (DB resource) -- customer has mailed to replace him. | Node JS, Android, iOS, ORACLE database , REST, API design, HTML, CSS, JavaScript, JSON, IIS/ Apache, Linux, Aadhaar Vault, NSDL PayGov, C-DAC | Bank account details in GeM portal & in invoice is different -- intimatedd sales to correct the same. Replacement of Vikas Kohli (DB resource) -- customer has mailed to replace him. | 2025-07-25 | 13.78% | 11.94%
4 | ECCS | West | Application Maintenance | 2427.0573 | 1930.7362 | 0 | 1930.7362 | 50 | 496.3211 | -10.3496 | 0 | 3 years incl. 3 month HOTO | 79.55% | Quarterly | Start Date (PO) : 01-Dec-21 :: End Date (PO) : 31-Mar-25 | 0 | 165 L + 4 L | Application Support, Onsite support Helpdesk Operations and Maintenance Services and upkeep of the ECCS Application Transition of existing entire ECCS Application operations from the incumbent vendor Takeover and manage ECCS helpdesk & Trade helpdesk operations Manage and deliver current and proposed CRs Deployment of Project Management software tools as per RFP 95% of tickets to be addressed by Onsite team PO Amt in Lakh – 2184 {1820 + 364 (ramp-up)} Extension PO – 242.7 L (for 4 month till 31st Mar 2025} | Transition completed for ECCS 2.0 from 1st Jan’25 till 14th Feb'25 JAS’24 Payment received. 12L short payment. Mail has been initiated. Follow up going on from Sales team Extension received till 31st Mar 2025 on 28th Jan for 242.7 L Exit phase (1st Jan 25 to 14th Feb 25) invoicing done of 82 L. OND’24 Payment of 182 L received on 29-Mar-2025 84 L billed from Ramp-up cost (CST + Helpdesk). | Transition phase completed on 31-Mar-2025. Collection of due payments. Collection of 12 L short payment. SLA data for Exit phase uploaded on 08-Apr-25. MA tracker received, replied with artifacts & approvals. Exit phase invoice payment of 72 L received on 14-Jul-25 | Java Struts | 0 | 2025-07-14 |  | -17.63%
5 | ECCS NEW | West | Application Maintenance | 2413.026 | 399.2692 | 91 | 490.2692 | 471 | 2013.7567 | 399.2692 | 0 | 2 years (incl. 3 month HOTO) | 16.55% | Quarterly | Start Date (PO) : 26-Sep-24 :: End Date (PO) : 25-Sep-26 | 68 | 287.27 L | Application Support, Onsite support Helpdesk Operations and Maintenance Services and upkeep of the ECCS Application Manage and deliver current and proposed CRs Deployment of Project Management software tools as per RFP Technological Upgradation of ECCS application The vendor is responsible for ECCS application technological upgrade. Application Upgrade Version Upgrade Architecture Upgrade User Interface Upgrade | Revised SLA methodology document shared and meetings ongoing to finalize Feb’25-Mar’25 & AMJ25 bills submitted, data upload pending as PGA informed to finalize SLA document. POC on new technology upgrade has been completed and VAPT initiated. Approval received for SLA 4.8 -- henceforth TCS tickets for shifting traffic will not be logged under ECCS. (25-Jun-25), which were creating change in severity. | SLA methodology to be finalized with Customer to avoid penalties. SLA methdology finalisation discussions in progress with PGA & WZU. On-boarding of 1 Java Developer. Ramp-up requirement for tech upgrade + NCTC resource to finalise. Review JAS-25 Saadhit plan and take WZU agreement as multiple activities ongoing. Implement CR's in JIRA -- to automate SLA computation for enhancement related SLA's Attendance system changes to be done from TCS -- followup ongoing CSAT automated mails follow-up. SLA clock changes for 5.3 from 24hours to 16 hours (WZU approved, awaiting changes in HPSM) | Java Struts, For upgrade - TBD | Onboarding of 1 java developer | 2025-07-23 | 41.25% | 33.03%
6 | PFRDA | North | Software Development | 1265.6947 | 435.4656 | 0 | 435.4656 | 367 | 830.2291 | 0 | 0 | 1 yr Proj + 1 Yr Warr + 4 Yr AMC | 34.41% | 10% SRS ( 2m), 10% UAT( 7m), 10% VAPT/Audit ( 8m), 50% Implementation (9m), 10% training( 10m), 10% final Go-live ( 12m) for Solution cost of 622 L | Start Date (PO) : 18-Dec-23 :: End Date (PO) : 17-Dec-29 | 26 | As per achievment | Design, development, implementation and maintenance of PFRDA intranet portal(PINTRA) - internal digitalization (HRMS and finance) along with mobile app for HRMS Modules – HRMS, Finance, Admin, Legal, IT Management System 9 months Go-Live + 3 months Stabilisation + 1 Year Warranty + 4 Years AMC Payment Milestone : 10% SRS ( 2m), 10% UAT( 7m), 10% VAPT/Audit ( 8m), 50% Implementation (9m), 10% training( 10m), 10% final Go-live ( 12m) for Solution cost of 622 L Quarterly Payment for below; FMS during Warranty – 0.5 L / Qtr for 4 Qtr = 2 L MeitY empanelled GCC / VPC – 13.5 L/Qtr for 20 Qtr = 271 L Support Payment for Operations – 17.6 L/Qtr for 20 Qtr = 354 L CR – 17 L as & when required | System study / SRS/ FRS; UAT & implementation for payment milestones completed. Same is billed & payment collected for SRS & UAT milestone. GitHub & JIRA implemented. Go-Live done on 19th May 2025. Helpdesk set-up done. Mobile App (1) –Complete. iOS app will be shared after dev account is received. | Bug fixes & service support. (UAT Feedbacks Admin - 40, Legal- 25, HRMS-588) -- timeline to be provided to PFRDA. Odoo licences to be provided to PFRDA. Daily stand-up meetings to be started which includes PM. Also 7 key resource should seat at PFRDA for 1 month -- requested by PFRDA as per meeting on 23rd July between CMS & PFRDA leadership. VAPT to be done, after incorporating UAT feedback points. Training to users. Payment collection for implementation milestone. Billing for remaining milestones. | Spring Boot, Odoo, React JS, Apache, PostgreSQL, Postman, Moodle, Figma, Ubuntu, AWS Cloud, Flutter, React, Node JS | Odoo licences to be provided | 2025-07-24
7 | DIC NHAI | North | Software Development | 2186.28 | 162.75 | 176 | 338.75 | 154 | 2023.53 | 162.75 | 0 | 3 Years | 7.444% | Track 1 (2m) - 10%, Track 2 (4m) – 20%, Track 3 (6m) – 20%, 8m – 50% | Start Date (PO) : 13-Nov-24 :: End Date (PO) : 12-Nov-27 | 36+9 | As per achievment, Phase 1 - 321 L | Developing and Maintaining a state-of-the-art Application to support transaction-based business processes covering entire lifecycle of National Highway projects of NHAI – Data Lake 2.0 upgradation. Payment Phase & milestone wise Track 1 (2m) - 10%, Track 2 (4m) – 20%, Track 3 (6m) – 20%, Track 4 (8m) – 50% Every phase of 6 months. Deployment of proposed 33 resources. (+5 in phase 2) | DIC team along with CMS team working on this project Total 9/10 modules KT received. Drone module BRD yet to finalise. 7/9 – development complete. UAT Done. After initial failed demo, second Demo for developed 7 Modules with bug fixing & feedback resolution completed on 16-Jun-2025. Demo at NHAI offices - Dwarika, Gaziabad, sohna, bagpat, Faridabad, Jaipur done. changes after security audit are being implemented. Go-live of 7 completed modules done on 17th Jul 2025. -- awaiting official sign-off. | Remaining resource on-boarding of Helpdesk (1 YTJ + 1 open position) Testing of remaining 2 modules - Road Safety Audit & toilet Maintenance. Next Phase-2 modules decision -- onboarding & payment module discussion done. Brics module requirement discussion to be done. Post Go-live activities -- SOP creation of helpdesk support, user manual etc. | No-SQL, Ruby, Python, Java, HTML, CSS, JavaScript, Angular, React, GIS/ML, Cloud - TBD, Node JS, Rest API | 0 | 2025-07-25 | 34.15% | 32.59%
8 | DAnFW | North | Application Maintenance | 1606.08 | 361.3899 | 65 | 426.3899 | 171 | 1244.6901 | 249.8643 | 0 | 2 Years | 22.5% | Monthly | Start Date (PO) : 05-Dec-24 :: End Date (PO) : 04-Dec-26 | 50+2+2 | 67.88 L | Deployment of technical resources for application development, customization and maint. for ‘digital agriculture division, DA&FW’ Deployment of required 34 resources. 1 resource each – Team Lead, Sr. Mobile Dev., tester, BA, content management expert. 2 resource each – Full stack/Sr. Dev., UI/UX, API dev., mobile dev., dashboard expert, e-office support 3 resource each – Sr. Front end dev, VC support 5 resource – Full stack dev. (>6 to <10 yrs.) 6 resource – Full stack dev. (>3 to <6 yrs.) Deployment of 16 resources on need basis. | 35 resources onboarded out of 35, including 1 additional Team Lead approval from customer. 15 resources onboarded out of 15 – additional on need basis approval received from customer. 2 VC Support addnl order received -- onboarded. 1 Drupal & 1 SEO developer onboarded on temporary basis (FOC basis) Billing till Jun-25 done. Payment of 127 L received on 27-Jun-2025 (till Apr-25) 1. KM – Consuming SHC data through API provided by division. First developing the module for showing the data. 1.1 User Management – Surveyor level Data target set. Now start progress report on senior profile 1.2 Understading new UM portal design 2. Natural Farming : 2.1 Developing Edit/Delete functionality 2.2 Working on Client observation points. 3. NFSM – Hold due to KKMS portal launching 4. Agristack- DCS new design development started. 5. KKMS – Portal has launched today, so doing demo. 6. Concurrent – Doing work on observations 7. Inventory – Project done. Now deploying on client system locally. They will connect it on server 8. Krishi Unnati –Working on last 2 models. | Agristack – Showing the progress to Division NFSM – Resume working on API consuming KM- GIS – Cluster count API development will start, Improve speed KM-UM – Adding and giving Export option in NMEO-OP on Agencies. NF – Starting working on Given Observation points KYS - Deliver next week Inventory – changes to complete by 15th. Concurrent – Project review by client | C#, ASP.NET, MVC, .NET Core, Visual Studio, HTML5, CSS3, RESTful API, MERN, flutter, react Native, MS SQL, e-Office | 0 | 2025-07-24 | 11% | 11%
9 | GWALIOR SC ICCC | West | Smart City | 1372.5806 | 397.1004 | 34 | 431.1004 | 204 | 975.4802 | 41.283 | 0 | 62 month (incl. 2 mnth HOTO) | 28.93% | FMS – 11 L + Taxes (monthly billing) O&M – 13 L + Taxes (quarterly billing) Audit – 8 L + Taxes (yearly billing for 1st Year) Upgradation – 324 L + Taxes (60% - 194 L) | Start Date (PO) : 30-Aug-24 :: End Date (PO) : 31-Oct-29 | 33+1 | As per milestone | ICCC & DC upgradation with 5 years comprehensive AMC – 60% on SITC & 2% every Quarter with O&M payment CAMC of existing IT & non-IT infra - quarterly payment Manpower services: 39+1(non-billable) – monthly payment ICCC certifications – Yearly payment Provision – as & when required. | ICCC and upgradation of IT and non IT infra. Project earlier managed by HP. CMS O & M started from 1st October 24 HOTO & GAP report submitted on 30th Sep & acknowledgement copy received from Customer. FAT & UAT completed & sign-off received. 33 manpower deployment done. ICCC & DC upgradation component approval recd. & material delivered at site. Payment of 240 L received. + 117 L received on 4th July. Manpower & O&M Invoice submitted to client. Billing done till Apr-25 & AMC Q2 (FMA-25). Invoicing for upgradation milestone done 324 L. Installation complete. Jun25 manpower draft invoice submitted to customer. | Maintenance activities. ISO Certification - consultant is on site & work is in progress Critical issues list identified and shared to HO. New Switch, Router, WLD display - in progress. Insurance to be renewed. Min wages letter to be submitted to client. | NA | Min wage hikes for resources - poses a risk | 2025-07-25 | 19.54% | 11.44%
10 | Kanpur SC O&M | North | Smart City | 5337.5 | 3431.25 | 508 | 3939.25 | 916 | 1906.25 | 762.5 | 0 | 42 month | 64.29% | Quarterly | Start Date (PO) : 01-Jan-23 :: End Date (PO) : 25-Jun-26 | 31 + 2 + 14(TP) | 381 L | O&M support, AMC of all BOQ. Maintenance of Hardware, Network, Software, ICT Infrastructure, L1 , L2, L3 & OEM Support of all field solutions, DC & DR and applications for 42 months ( 50 junctions ) BG for 762 L to be submitted, advance payment of 2 Qtrs will be released after signing SOW. BG would be returned back to CMS after 4 Qtrs. PBG of 3% of balance of TCV (137 L) to be submitted at end of Qtr 4. | Jan 23 to Mar 25 (Total 9 quarters payment released-75%). 24 July meeting scheduled with commissioner to discuss issues related to ICCC critical issues & withold payment -- KSCL will not pay to TechM (re-imbursement) & has to be paid by TechM to CMS Billing done for OND24 & JFM25 Qtr. Neat-Park application demonstration to client is carried out on 23rd Oct 2024. Client has suggested few points, Team has incorporated the same in .Payment integration is in progress (Bank details awaited from client - will share after VAPT). -- VAPT in progress. EMS OEM onboarding done - OEM Team repairing work in progress. Collected ~ 632 L till JFM-25 | Smart Parking- Payment integration is in progress.(bank details awaited) -- after VAPT Security Workshop to be conducted, Renewal of Licenses afterwards. Reimbursement of recurring charges from TechM Release of 25% retention/withheld amount -- In progress. | NA | Delay in release of withheld amount (25%), recurring charges reimbursement. | 2025-07-25 | 25% | 51.23%
11 | NMPT | South | CRP | 680.6929 | 239.8516 | 15 | 254.8516 | 241 | 440.8414 | 20.7468 | -2.0913 | 5 years | 35.24% | Monthly | Start Date (PO) : 01-Jul-24 :: End Date (PO) : 01-Jul-29 | 15 | 7.3 L | Operation and Comprehensive annual Maintenance Contract (CAMC) of the RFID System for a Period of 5 years at NMPA. FMS – 12 data entry operators, 2 Technician, 1 Service Engineer Replacement of existing Infrastructure in 1st year. – 197 L (inc. KK & Cruise gate augmentation). Payment within 15 days after SITC of replacement. Integration with existing system. | Support Started from 1st July 2024. Installation is complete for FRS & UHF system for main gate. Received WO for kk & cruise gate on 3rd Oct 24, to be completed in 3 months (03-Jan-2024)-- Taken exclusion as both Gates not ready. KK Gate - 2 lanes system installed on temporary basis. Cabling provision is done for installation at both KK & cruise gate. CAMC Billing done till May-25. | Regular maintenance activities. Support activities after Go-Live of UHF Reader, HF Reader, and FRS applications, Go-live expected. Payment collection for existing infra part after Go-Live. (~159 L) Payment collection for Feb-25 to May-25 CAMC invoices. | NA | 0 | 2025-07-25 | -11.87% | 12.04%
12 | Vadodara Traffic | West | Smart City | 1045.7627 | 709.4025 | 0 | 709.4025 | 0 | 336.3602 | -0.5941 | 0 | SITC 4 Mths & O&M - 5 Yrs | 67.84% | After SITC | Start Date (PO) : 26-Feb-24 :: End Date (PO) : 25-Jun-29 | 1 (Shared) | full | Design, supply, Erection testing & commissioning of traffic signal at various 28 junction. Upgradation of old traffic signal at 44 Junction. Integration with existing system. 5 year comprehensive maintenance service. Payment 100% after successful installation. | Site survey done for all 28 Junction and submitted to Client VMC approval received for SIT at all 28 Locations. 28/28 Junction made Live. O & M from 1st Feb 2025 reveived. 10/44 Jn upgradation permission received. 10/10 upgradation completed. Balance location -- 302 Aspects additional to be supplied -- awaiting material (EDD - Tentative 20 Aug) | Field work for remaining locations, after approval. O&M started from 01 Feb 2025. - support activities. First Qtr billing(~8 L) after Capex final billing (~47L) -- after aspects delivery. | NA | 0 | 2025-08-01 | 18% | 18%
13 | VADODARA ICCC | West | Smart City | 2019.8763 | 245.7814 | 0 | 245.7814 | 0 | 1774.095 | 84.9446 | 0 | 5 years | 12.17% | Quarterly | Start Date (PO) : 01-Aug-24 :: End Date (PO) : 31-Jul-29 | 7 +10(shared) / 17 | 100.99 L | O&M support, AMC of all BOQ. Maintenance of Hardware, Network, Software, ICT Infrastructure, L1 , L2, L3 & OEM Support of all field solutions, DC & DR and applications for 60 months Deployment of manpower : Project Manager (1), Technical Expert (4) [Network and Security, Video management, server-storage, CCC software], Electrician (4), Field staff (8) PBG of 3% | Contract agreement signed . PBG of 3 % submitted All resources has onboarded. BOM and other detail shared with purchase team for finalization of contract. First Qtr payment received ~ 80 L on 28-May-25 Third quarter invoice submitted. | Start maintenance activity as per SLA Third quarter invoice submitted. Payment collection. (2nd & 3rd Qtr) | NA | 0 | 2025-08-01 | 20.49% | 20.46%
14 | ISCDL | West | Smart City | 2903.0413 | 1722.0306 | 0 | 1722.0306 | 977 | 1181.0107 | 54.8212 | 0 | SITC – 9 M, O&M – 5 Yr | 59.32% | Quarterly | Start Date (PO) : 01-Nov-22 :: End Date (PO) : 31-Aug-29 | 6 | 43.3 L + Taxes (O&M) | Implementation of (ITMS) for 50 Junctions with Centralised Monitoring + 50 additional services Payment Milestone wise 5% Inception Report, 10% requirement Study, 30% material delivery & commissioning of 1 corridor ( 15 Junctions ) , 30% remaining delivery ( 35 junctions + 20 SVD + 20 ATCC and 10 TVD ) & commissioning, 25% Go Live. O & M : 5 Years CAPEX ~20.37 Cr & OPEX ~ 8.66 Cr | Phase-1 of 14 Junctions are Live – Payment collected (1039 L) Phase-2 – 16 Junctions completed & invoices submitted for payment. Phase-3 –10 Junctions and 44 Locations delivered & invoices submitted for payment. Revised CAPEX now capped at 16Cr for work completion and payment processing. Junction & Location on hold are removed from Capex calculation Reimbursement claims submitted for payment collection. O & M requested from 1st Sep 2024. Collection for due payments approx. 500 L – Phase 2 and 3 along with electricity and connectivity reimbursement New project of approx 600 L is expected by mid of July. | Go-Live & O&M maintenance activities. Payment collection 243 L Capex + 110 L misc payment. | NA | 0 | 2025-07-17 |  | -20.41%
15 | ISCDL server | West | Smart City | 227.9543 | 201.1313 | 0 | 201.1313 | 0 | 26.823 | 2.2353 | 0 | - | 88.23% | - | - | - | - | - | - | - | - | - |  |  | 49.96%
16 | IREL | West | Software Development | 1047.3631 | 162.9668 | 19 | 181.9668 | 115 | 884.3963 | 0 | 0 | SITC – 12 Months , O&M - 4 Yrs | 15.56% | Milestonewise | Start Date (PO) : 29-Oct-18 :: End Date (PO) : 30-Sep-25 | 23 | As per Achievement | Development of Integrated ERP System (IITS) (326 L) FMS including support & maintenance (147 L) Cloud Services (574 L) Change Request (63 K) | 1. April Payroll Re-run for HO Employees - Re-processed April payroll for 6 Head Office employees and shared the updated payslips along with IT computation details with the client.​ 2. Income Tax Review and Issue Resolution - Reviewed income tax calculations to identify discrepancies related to perquisite tax, employee declarations, computation logic, and components considered under annual gross salary. Shared findings with Pranesh and Kailash. Multiple issues have been successfully addressed and resolved.​ 3. CMS Email ID Configuration for Attendance - Followed up with IREL to update the CMS email ID for receiving daily attendance data across all units. Despite escalation by IREL's Nirdesh Kumar, no updates have been received yet.​ 4. TA/DA Module Demo - Conducted a demo of the TA/DA module for IREL HR representative Mr. Mohit Jain | 1. May a. Income Tax Discrepancy Discussion with IREL Payroll Team - Share our detailed tax calculation in Excel format to help identify discrepancies in perquisite tax computation.​ 2. Resolution of Remaining Income Tax Computation Issues - Continue efforts to resolve outstanding issues related to income tax declarations and mismatches in annual gross salary components.​ 3. Ongoing Client Support and Coordination - Provide continuous support to the client by resolving queries, clarifying payroll-related processes, and assisting in workflow improvements.​ | Core Java, BIRD tool, postgre, ESDS cloud | 0 | 2025-07-25 |  | -955.1%
17 | Guwahati SC | East | Smart City | 669.1843 | 577.6653 | 0 | 577.6653 | 325 | 91.519 | 262.5109 | 0 | 1 Year + O&M | 86.32% | 10% of capex - Submission of Survey report, built report, project deployment plan. 50% - supply of material on pro-rata basis 15% - installation of material on pro-rata basis 15% - commissioning on pro-rata basis 5% - Go-live on pro-rata basis for individual system 5% - Overall Go-live of complete project. | Start Date (PO) : 10-Feb-25 :: End Date (PO) : 09-Feb-26 | 1 | As per Achievement | SITC -- 20 ECB, 20 PA, 10 ENV SENSOR, 10 VMD, 1 GIS Software 5 years O&M | Site Survey done & report submitted to customer. GIS software invoicing done 315 L & installation completed. Configuration in process. (SRS & FRS finalisation awaited) PA, ECB, EVS, EVS Poles (10 nos.) materials delivered EVS, PA-ECB, GIS, VMS software delivered. 1. Change request letter for VMD submitted by Honeywell to GSC -- approval received. 2. VMD Structure & Pole drawing approved by GSC. 3. EVS pole foundation 10/10 ready. Pole will be installed after curing. 5. Warehouse finalization done. 340 L received on 22-May-25. | 1. EVS pole installtion after curing. 2. ECB encloser foundation also pending due to J-bolt and template unavailable as on date. 3. ECB encloser, VMD display (expected 27-Jul), VMD pole & structure, Cables and accessories to be delivered. 4. FRS & SRS for GIS software to submit -- In progress (under PMC review). 5. Collection of due payment ~106 L. 6. VMD structure J bolt will be received by 28-Jul. | 0 | 0 | 2025-07-25 | 20% | 20%
18 | Chennai Port - Video Wall | South | CRP | 242.5721 | 223.5721 | 0 | 223.5721 | 0 | 19 | 0 | 0 | 60 Days + 1Yr Warr + 3Yr AMC | 92.17% | Supply of all materials - 40% Installation and integration with CCTV Surv. Centre & Port Command Centre - 30% Handover, Training & uninterrupted operation of min 15 days - 30 % | Start Date (PO) : 12-Mar-25 :: End Date (PO) : 11-May-25 | 0 | 100% of Material & Installation cost | SITC -- Video Wall, AV Controller, Fire Alarm System, Access Control System (ACS), Networking Points and UPS Interface with Port Command Centre and CCTV Surveillance Centre Project Management Training and Documentation 1 Year Warranty 3 Year AMC | All work completed. Go-Live completed on 23-Apr-2025. Received 100 % payment as per milestone. Payment as per milestone Supply of all materials - 40% - received on 11-Apr-25 of Rs. 109 L Installation and integration with CCTV Surv. Centre & Port Command Centre - 30% received on 02-May-25 of Rs. 77.33 L Handover, Training & uninterrupted operation of min 15 days - 30 % received on 23-May-25 of Rs. 77.33 L | Warranty support activities by vendor | 0 | 0 | 2025-05-26 |  | 8%
19 | MCS - L&T | West | Smart City | 437.1641 | 361.0247 | 72 | 433.0247 | 171 | 76.1394 | 361.0247 | 72.5692 | 6 months | 82.58% | Monthly | Start Date (PO) : 01-Mar-25 :: End Date (PO) : 31-Aug-25 | 228 | 72.86 L | Viewing Manpower in 4 shifts including backup to cover 203 shifts daily. | Billing for Mar-25 to Jun-25 done. | Daily Operators shifts support. | 0 | 0 | 2025-07-25 | 52.93%
20 | JNPA | West | EMS | 171.3136 | 0 | 0 | 0 | 0 | 171.3136 | 0 | 0 | 6 months + 5 Yr CAMC | 0% | Product Cost Payable on Product Delivery - 70% ICT Charges - 30% | Start Date (PO) : 07-Apr-25 :: End Date (PO) : 04-Oct-25 | 1 (shared) | 131.78 L | Design, Supply, Installation, Testing and Commissioning of web based enterprise energy and utility Management system with five years of Comprehensive Annual Maintenance Contract (CAMC) a) Complete built in energy monitoring system including power distribution monitoring of electrical & utility energy & consumption monitoring viz boundary level, process level and specific identified key areas. b) Demand management system that covers demand forecasting, scheduling and deviation monitoring w.r.t the schedule drawl c) Energy billing system that coverers consumer’s energy monitoring and billing #>Functional Requirements/ Deliverables : DATA ACQUISITION SYSTEM // DATA MANAGEMENT SYSTEM // DEMAND FORECASTING MODULE // Deviation Settlement Mechanism Module //Demand Management Module // Utility Billing Module – Electricity, Water & Rental #>Infrastructure Requirements: Server // Cloud Service (IaaS) // OS // DB // Networking | Material ordered & Most of the materials received. Awaiting delivery of water meter (expected 21-July-25), ABT Meter (expected 30-Jul-25) to start installation work. Data required by software team is collected & provided to stakeholders for further process. | Start of installation activity from 21-Jul-25 | 0 | 0 | 2025-07-25