## Data_summary
SN | Project | Region | Type | Total PO Amt | Billed Till Date | Accrual | Total Revenue | Open AR | Open Billing | Billed YTD_FY25-26 | Current Month Billing | Project Duration | Billed | Billing Milestone | Project Dates | Resource | Milestone billing amount | Scope | Overall Progress | Weekly Plan | Technology / tools | Challenges / Risks | Update Date | Profit_YTD MIS | Profit_FY24-25_MIS
1 | INVEST INDIA | North | Application Maintenance | 840.2445 | 564.1 | 23 | 587.1 | 83 | 276.1445 | 116.7006 | 23.3401 | 36 Months | 67.14% | Monthly | Start Date (PO) : 17-Jul-23 :: End Date (PO) : 16-Jul-26 | 15 | 23.34 L | Hiring of Professionals for --. Application Development and Maintenance – 36 months. Front End and Back End developer – 8 Resources. Full Stack developer, Solution Architect, QA Engineer, UI/UX designer, business analyst, QA automation tester, Project Manager – 1 resource each. | Monthly billing from Jul-23 to Aug-25 done. Application maintenance and regular CR deployment. 355 tasks out of 408 tasks are in production as on date. Pragati meetings module is developed by CMS - These meetings are being chaired by Prime Minister of India. AWS Optimization has been done on all PMG environments as instructed by PMG team. Security Audit was done & agency has raised total 26 points, out of which 7 high priority tasks are completed & awaiting further action from Auditor. Customer wants AI module to be integrated, pitching our AI solution & will get additional order if selected. | Maintenance activities :. Deployment of 2 task -- on UAT. 14 Tasks In progress (+ 9 Tasks in QA Testing, +3 in designing, +11 under estimation & + 14 Tasks in to do). Due payment collection (May to Aug 25). Replacement of Bimal Kalsa on priority. | NodeJS , HTML5/CSS , JS , React , Springboot Elastic, PostGreSQL , MySQL , MongoDB, Postman, API & SSO integration | Replacement of Bimal Kalsa (Backend+Elastic Developer) - As per rfp terms we need to provide replacement with overlapping period of 30 days, if not then penalty equivalent to monthly amt of resource will be deducted. | 2025-09-06 | 58.01% | 43.23%
2 | SBM-U | North | Application Maintenance | 1305.45 | 680.7992 | 36 | 716.7992 | 92 | 624.6508 | 181.3125 | 36.2625 | 36 Months | 52.15% | Monthly | Start Date (PO) : 10-Jan-24 :: End Date (PO) : 09-Jan-27 | 7+13 (GAIA) | 36.26 L | Development, Maintenance and operations of an Integrated Portal for SBM used by the MoHUA Update and maintain the various modules and functionalities developed as a part of the “Integrated Swachhatam” portal update and maintain all mobile applications developed Resolve all the bugs, issues and queries raised for these developed functionalities | 20 resources on-boarded (13 resources from GAIA – Tech Partner). Payment received till May’25. Invoicing done till Jul’25. Daily Waste Reporting mobile app made live for pilot of 50+ ULB’s. Campaign ‘SABB 2_0’ is Live. UWM Dashboard development done - addition of FSTP plant & SOAK on ULB login in progress. EOI Form testing complete - through which volunteer's can register themselves to work for SBM. New SSJ (Swachh Survekshan Jodi) page created for City pairing on website - in this one weak & one strong city (on scores of swachh survekshan) will be paired & they will cordinate to improve their processes. | Maintenance activities:. Daily ULB support, Website changes ongoing. Support to GFC & ODF-Field Assessment ongoing. Issue Resolution. Dashboard revamp in portal. SS Handover planned with IPSOS in the next week. | Angular, AWS Cloud, mySQl, Posgresql, NodeJS, Java, MongoDB, RESTAPI, HTML, PHP, MicroService, Quicksight,CSS, Flutter | 0 | 2025-08-28 | 19% | 19%
3 | ORGI | North | Application Maintenance | 849.8214 | 368.4548 | 65 | 433.4548 | 38 | 481.3666 | 114.9403 | 29.4055 | 2 Years | 43.36% | Monthly | Start Date (PO) : 02-Apr-24 :: End Date (PO) : 01-Apr-26 | 26 + 1 | 35.2 L | Maintenance, operations & enhancement of ORGI CRS Web and Mobile Application(s) including migration of legacy data from State CRS applications to ORGI CRS and vice-versa through APIs. Resources for 2 years as below – Data Analytics, Database Administrator, Mobile App. Developer Android, Mobile App. Developer iOS, System Admin, Team Lead/Technical Project Manager, Training and Change Management Engineer, UI / Web Designer - 1 resource each. API Developers, Quality Assurance/ Test Engineer, Senior Application Developers – 2 resource each Application Developers, Technical Support (helpdesk) – 6 resource each | Kick-off meeting with Customer done. Infra provided to resources by ORGI. Shadow & reverse Shadow phase completed. Independent development – Started & In Progress. KT Activity – Completed. Handover from HPE current SI: Completed. Billing done from Apr-24 till Jun-25 ( New rates applicable from 2nd April 25). Received payment till Apr25. Daily Birth/Death count monitoring report - automation done. Addition of Download link for the android app on communication email for RE/SR done. Provision to authenticate the Aadhaar number for RE/SR done. iOS App Live in App Store. Correction in Adoption Case done. Bihar Jurisdiction splitting done -- data shifting in progress. Provision made for General Public -- can now download birth & death certificate for self & family (adhar authenticated). Replacement of Vikas Kohli (DB resource) -- Roopali Goel joined on 13th Aug. | 4 states will join CRS portal (all certificates will be issued from CRS) -- Gujarat, Pondicherry, Telangana & Delhi. Gujarat onboarding to be completed by 15th Aug -- now extended till 31st Aug. Registrar payment reconciliation report work in progress. Audit log - for cyber forensics in case of fraudulent certificate generation. eSign on Android App. Billing for Jul-25 after client approves attendance. Indore IMC Zonal registar creation. | Node JS, Android, iOS, ORACLE database , REST, API design, HTML, CSS, JavaScript, JSON, IIS/ Apache, Linux, Aadhaar Vault, NSDL PayGov, C-DAC | 0 | 2025-08-28 | 22.61% | 11.94%
4 | ECCS | West | Application Maintenance | 2427.0573 | 1930.7362 | 0 | 1930.7362 | 50 | 496.3211 | -10.3496 | 0 | 3 years incl. 3 month HOTO | 79.55% | Quarterly | Start Date (PO) : 01-Dec-21 :: End Date (PO) : 31-Mar-25 | 0 | 165 L + 4 L | Application Support, Onsite support Helpdesk Operations and Maintenance Services and upkeep of the ECCS Application Transition of existing entire ECCS Application operations from the incumbent vendor Takeover and manage ECCS helpdesk & Trade helpdesk operations Manage and deliver current and proposed CRs Deployment of Project Management software tools as per RFP 95% of tickets to be addressed by Onsite team PO Amt in Lakh – 2184 {1820 + 364 (ramp-up)} Extension PO – 242.7 L (for 4 month till 31st Mar 2025} | Transition completed for ECCS 2 from 1st Jan’25 till 14th Feb'25. JAS’24 Payment received; 12L short payment - Mail has been initiated; Follow up going on from Sales team. Extension received till 31st Mar 2025 on 28th Jan for 243 L. Exit phase (1st Jan 25 to 14th Feb 25) invoicing done of 82 L. OND’24 Payment of 182 L received on 29-Mar-2025. 84 L billed from Ramp-up cost (CST + Helpdesk). Exit phase invoice payment of 72 L received on 14-Jul-25. | Collection of due payments & 12 L short payment. | Java Struts | 0 | 2025-08-28 |  | -17.63%
5 | ECCS NEW | West | Application Maintenance | 2413.026 | 399.2692 | 91 | 490.2692 | 471 | 2013.7567 | 399.2692 | 0 | 2 years (incl. 3 month HOTO) | 16.55% | Quarterly | Start Date (PO) : 26-Sep-24 :: End Date (PO) : 25-Sep-26 | 68 | 287.27 L | Application Support, Onsite support Helpdesk Operations and Maintenance Services and upkeep of the ECCS Application Manage and deliver current and proposed CRs Deployment of Project Management software tools as per RFP Technological Upgradation of ECCS application The vendor is responsible for ECCS application technological upgrade. Application Upgrade Version Upgrade Architecture Upgrade User Interface Upgrade | Revised SLA methodology document shared and meetings ongoing to finalize Feb’25-Mar’25 & AMJ25 bills submitted, data upload pending as PGA informed to finalize SLA document. POC on new technology upgrade has been completed and VAPT initiated. Approval received for SLA 4'8 -- henceforth TCS tickets for shifting traffic will not be logged under ECCS (25-Jun-25), which were creating change in severity. SLA clock changes for 5'3 from 24hours to 16 hours (WZU approved) & changes done in HPSM. | SLA methodology to be finalized with Customer to avoid penalties - SLA methdology finalisation discussions in progress with PGA & WZU. Ramp-up requirement for tech upgrade. Implement CR's in JIRA -- to automate SLA computation for enhancement related SLA's Attendance system changes to be done from TCS -- followup ongoing CSAT automated mails follow-up. Collection of due payment. | Java Struts, For upgrade - TBD | Onboarding of 1 java developer | 2025-08-28 | 41.62% | 33.03%
6 | PFRDA | North | Software Development | 1265.6947 | 435.4656 | 0 | 435.4656 | 367 | 830.2291 | 0 | 0 | 1 yr Proj + 1 Yr Warr + 4 Yr AMC | 34.41% | 10% SRS ( 2m), 10% UAT( 7m), 10% VAPT/Audit ( 8m), 50% Implementation (9m), 10% training( 10m), 10% final Go-live ( 12m) for Solution cost of 622 L | Start Date (PO) : 18-Dec-23 :: End Date (PO) : 17-Dec-29 | 26 | As per achievment | Design, development, implementation and maintenance of PFRDA intranet portal(PINTRA) - internal digitalization (HRMS and finance) along with mobile app for HRMS Modules – HRMS, Finance, Admin, Legal, IT Management System 9 months Go-Live + 3 months Stabilisation + 1 Year Warranty + 4 Years AMC Payment Milestone : 10% SRS ( 2m), 10% UAT( 7m), 10% VAPT/Audit ( 8m), 50% Implementation (9m), 10% training( 10m), 10% final Go-live ( 12m) for Solution cost of 622 L Quarterly Payment for below; FMS during Warranty – 0.5 L / Qtr for 4 Qtr = 2 L MeitY empanelled GCC / VPC – 13.5 L/Qtr for 20 Qtr = 271 L Support Payment for Operations – 17.6 L/Qtr for 20 Qtr = 354 L CR – 17 L as & when required | System study / SRS/ FRS; UAT & implementation for payment milestones completed. Same is billed & payment collected for SRS & UAT milestone. Go-Live done on 19th May 2025. Helpdesk set-up done. Mobile App (1) –Complete. iOS app will be shared after dev account is received. | Bug fixes & service support (UAT Feedbacks resolved : Admin - 0 out of 41, Legal- 21 out of 25, IT-10 out of 19, HRMS-529 out of 585, F&A-35 out of 50). Daily stand-up meetings started which includes PM; Also 7 key resource should seat at PFRDA for 1 month -- requested by PFRDA as per meeting on 23rd July between CMS & PFRDA leadership - the same is in process. VAPT to be done - VAPT environment created & shared with AKS IT for further process. Payment collection for implementation milestone. Billing for remaining milestones. | Spring Boot, Odoo, React JS, Apache, PostgreSQL, Postman, Moodle, Figma, Ubuntu, AWS Cloud, Flutter, React, Node JS | 0 | 2025-08-28
7 | DIC NHAI | North | Software Development | 2186.28 | 162.75 | 176 | 338.75 | 154 | 2023.53 | 162.75 | 0 | 3 Years | 7.444% | Track 1 (2m) - 10%, Track 2 (4m) – 20%, Track 3 (6m) – 20%, 8m – 50% | Start Date (PO) : 13-Nov-24 :: End Date (PO) : 12-Nov-27 | 38+4 | As per achievment, Phase 1 - 321 L | Developing and Maintaining a state-of-the-art Application to support transaction-based business processes covering entire lifecycle of National Highway projects of NHAI – Data Lake 2.0 upgradation. Payment Phase & milestone wise Track 1 (2m) - 10%, Track 2 (4m) – 20%, Track 3 (6m) – 20%, Track 4 (8m) – 50% Every phase of 6 months. Deployment of proposed 33 resources. (+5 in phase 2) | DIC team along with CMS team working on this project Total 9 modules in part 1 & Total 8 modules in part 2 including Drone module (moved from part 1 to part 2). 9 out of 9 – development complete & UAT done for part 1. Go-live of 7 completed modules done on 17th Jul 2025 -- awaiting official sign-off. | Production deployment of remaining 2 modules - Road Safety Audit & toilet Maintenance. Next Part-2 modules decision -- requirement analysis in progress for 7 modules; yet to start for employee directory & drone module. Post Go-live activities -- SOP creation of helpdesk support, user manual etc. | No-SQL, Ruby, Python, Java, HTML, CSS, JavaScript, Angular, React, GIS/ML, Cloud - TBD, Node JS, Rest API | 0 | 2025-08-28 | 27.64% | 32.59%
8 | DAnFW | North | Application Maintenance | 1606.08 | 429.2679 | 65 | 494.2679 | 171 | 1176.8121 | 317.7423 | 67.878 | 2 Years | 26.73% | Monthly | Start Date (PO) : 05-Dec-24 :: End Date (PO) : 04-Dec-26 | 50+2+2 | 67.88 L | Deployment of technical resources for application development, customization and maintenance for ‘digital agriculture division, DA&FW’ Deployment of required 34 resources. 1 resource each – Team Lead, Sr Mobile Developer, tester, BA, content management expert. 2 resource each – Full stack/Sr Developer, UI/UX, API developer, mobile developer, dashboard expert, e-office support. 3 resource each – Sr Front end developer, VC support 5 resource – Full stack developer (>6 to <10 yrs.) 6 resource – Full stack developer (>3 to <6 yrs.) Deployment of 16 resources on need basis. | 35 resources onboarded out of 35, including 1 additional Team Lead approval from customer. 15 resources onboarded out of 15 – additional on need basis approval received from customer. 2 VC Support addnl order received -- onboarded. 1 Drupal & 1 SEO developer onboarded on temporary basis (FOC basis) Billing till Jul-25 done. Payment of 136 L received on 26-Aug-2025 (till Jun-25) 1] KM (Krishi Mapper) –. Applying Scheduler on Telangana State API for NMEO-OP. Developing new GIS Dashboard with New API. Optimizing current GIS Dashboard. GIS – Implemented Scheme table and graph. Implementing FY wise filter in GIS. Consumed Maha DBT API for onboarding on GIS. 2] Natural Farming -. Fixing users highlighted issue. Area Cover record on Home page - Done. 3] Krishi Unnati – Mother/Daily sanction module: Working. 4] Inventory – Project done. Customer has started feeding data & using it. | 1] NFSM – Make Agristack data live on Krishi Mapper. 2] KM -. Optimizing the API for performance improvement. GIS – Implementing FY, then data will reflect accordingly. Fixing UM bugs. 3] NF – . Work on Given Observation points. Implementing Area Covered & Cluster option. Providing Data Import option. | C#, ASP.NET, MVC, .NET Core, Visual Studio, HTML5, CSS3, RESTful API, MERN, flutter, react Native, MS SQL, e-Office | 0 | 2025-08-28 | 11% | 11%
9 | GWALIOR SC ICCC | West | Smart City | 1372.5806 | 397.1004 | 34 | 431.1004 | 204 | 975.4802 | 41.283 | 0 | 62 month (incl. 2 mnth HOTO) | 28.93% | FMS – 11 L + Taxes (monthly billing) O&M – 13 L + Taxes (quarterly billing) Audit – 8 L + Taxes (yearly billing for 1st Year) Upgradation – 324 L + Taxes (60% - 194 L) | Start Date (PO) : 30-Aug-24 :: End Date (PO) : 31-Oct-29 | 33+1 | As per milestone | ICCC & DC upgradation with 5 years comprehensive AMC – 60% on SITC & 2% every Quarter with O&M payment CAMC of existing IT & non-IT infra - quarterly payment Manpower services: 39+1(non-billable) – monthly payment ICCC certifications – Yearly payment Provision – as & when required. | ICCC and upgradation of IT and non IT infra; Project earlier managed by HP - CMS O & M started from 1st October 24. HOTO & GAP report submitted on 30th Sep & acknowledgement copy received from Customer. FAT & UAT completed & sign-off received. 33 manpower deployment done. ICCC & DC upgradation component approval recd & material delivered at site. Payment of 117 L received on 4th July. Manpower & O&M Invoice submitted to client; Billing done till Apr-25 & AMC Q2 (FMA-25), MJJ-25 PI submitted for Manpower & O&M. Invoicing for upgradation milestone done 324 L, Installation complete. | Maintenance activities. ISO Certification - consultant visited & required documentation work is in progress. Critical issues list identified and shared to HO - WLD (Water Leak Detection) display & AMC for - Tape Library, Server, Storage - in progress. Min wages letter to be submitted to client. Replacement of UI/UX devloper (Harsh Pathak - Resigned). | NA | Min wage hikes for resources - poses a risk. | 2025-08-29 | 19.54% | 11.44%
10 | Kanpur SC O&M | North | Smart City | 5337.5 | 3431.25 | 508 | 3939.25 | 916 | 1906.25 | 762.5 | 0 | 42 month | 64.29% | Quarterly | Start Date (PO) : 01-Jan-23 :: End Date (PO) : 25-Jun-26 | 31 + 2 + 14(TP) | 381 L | O&M support, AMC of all BOQ. Maintenance of Hardware, Network, Software, ICT Infrastructure, L1 , L2, L3 & OEM Support of all field solutions, DC & DR and applications for 42 months ( 50 junctions ) BG for 762 L to be submitted, advance payment of 2 Qtrs will be released after signing SOW. BG would be returned back to CMS after 4 Qtrs. PBG of 3% of balance of TCV (137 L) to be submitted at end of Qtr 4. | Jan 23 to Mar 25 (Total 9 quarters payment released-75%). 24 July meeting scheduled with commissioner to discuss issues related to ICCC critical issues & withold payment -- KSCL will not pay to TechM (re-imbursement) & has to be paid by TechM to CMS. Billing done for OND24 & JFM25 Qtr. Neat-Park application demonstration to client is carried out on 23rd Oct 2024; Client has suggested few points, Team has incorporated the same - Payment integration is in progress (Bank details awaited from client - will share after VAPT) -- VAPT completed & feedback points also closed on 28-Aug-25. EMS OEM onboarding done - OEM Team repairing work in progress. Collected ~ 632 L till JFM-25. | Smart Parking- Payment integration is in progress (bank details awaited) -- VAPT done & feedback points closed on 28-Aug-25. Reimbursement of recurring charges from TechM. Release of 25% retention/withheld amount -- In progress. | NA | Delay in release of withheld amount (25%), recurring charges reimbursement. | 2025-08-29 | 25% | 51.23%
11 | NMPT | South | CRP | 680.6929 | 239.8516 | 15 | 254.8516 | 241 | 440.8414 | 20.7468 | -2.0913 | 5 years | 35.24% | Monthly | Start Date (PO) : 01-Jul-24 :: End Date (PO) : 01-Jul-29 | 15 | 7.3 L | Operation and Comprehensive annual Maintenance Contract (CAMC) of the RFID System for a Period of 5 years at NMPA. FMS – 12 data entry operators, 2 Technician, 1 Service Engineer Replacement of existing Infrastructure in 1st year. – 197 L (inc. KK & Cruise gate augmentation). Payment within 15 days after SITC of replacement. Integration with existing system. | Support Started from 1st July 2024. Installation is complete for FRS & UHF system for main gate. Received WO for kk & cruise gate on 3rd Oct 24, to be completed in 3 months (03-Jan-2024) -- Taken exclusion as both Gates not ready from NMPT. KK Gate - 2 lanes system installed on temporary basis; Cabling provision is done for installation at both KK & cruise gate. CAMC Billing done till May-25. | Regular maintenance activities. Support activities for UHF Reader, HF Reader, and FRS applications; Official Go-live expected but payment for the milestone is received from NMPT (177 L ~ on 22-Aug-25). Payment collection for Apr-25 to May-25 CAMC invoices. | NA | 0 | 2025-08-29 | -25.97% | 12.04%
12 | Vadodara Traffic | West | Smart City | 1045.7627 | 709.4025 | 0 | 709.4025 | 0 | 336.3602 | -0.5941 | 0 | SITC 4 Mths & O&M - 5 Yrs | 67.84% | After SITC | Start Date (PO) : 26-Feb-24 :: End Date (PO) : 25-Jun-29 | 1 (Shared) | full | Design, supply, Erection testing & commissioning of traffic signal at various 28 junction. Upgradation of old traffic signal at 44 Junction. Integration with existing system. 5 year comprehensive maintenance service. Payment 100% after successful installation. | Site survey done for all 28 Junction and submitted to Client VMC approval received for SIT at all 28 Locations. 28/28 Junction made Live. O & M from 1st Feb 2025 reveived. 10/44 Jn upgradation permission received. 10/10 upgradation completed. Balance location -- 302 Aspects additional to be supplied -- awaiting material (EDD - Tentative 12 Sep) | Field work for remaining locations, after approval. O&M started from 01 Feb 2025. - support activities. First Qtr billing(~8 L) after Capex final billing (~47L) -- after aspects delivery. | NA | 0 | 2025-08-29 |  | 18%
13 | VADODARA ICCC | West | Smart City | 2019.8763 | 245.7814 | 0 | 245.7814 | 0 | 1774.095 | 84.9446 | 0 | 5 years | 12.17% | Quarterly | Start Date (PO) : 01-Aug-24 :: End Date (PO) : 31-Jul-29 | 7 +10(shared) / 17 | 100.99 L | O&M support, AMC of all BOQ. Maintenance of Hardware, Network, Software, ICT Infrastructure, L1 , L2, L3 & OEM Support of all field solutions, DC & DR and applications for 60 months Deployment of manpower : Project Manager (1), Technical Expert (4) [Network and Security, Video management, server-storage, CCC software], Electrician (4), Field staff (8) PBG of 3% | Contract agreement signed . PBG of 3 % submitted All resources has onboarded. BOM and other detail shared with purchase team for finalization of contract. First Qtr payment received ~ 80 L on 28-May-25 Third quarter invoice submitted. | Start maintenance activity as per SLA Third quarter invoice submitted. Payment collection. (2nd & 3rd Qtr) | NA | 0 | 2025-08-29 | 20.49% | 20.46%
14 | ISCDL | West | Smart City | 2903.0413 | 1722.0306 | 0 | 1722.0306 | 977 | 1181.0107 | 54.8212 | 0 | SITC – 9 M, O&M – 5 Yr | 59.32% | Quarterly | Start Date (PO) : 01-Nov-22 :: End Date (PO) : 31-Aug-29 | 6 | 43.3 L + Taxes (O&M) | Implementation of (ITMS) for 50 Junctions with Centralised Monitoring + 50 additional services Payment Milestone wise 5% Inception Report, 10% requirement Study, 30% material delivery & commissioning of 1 corridor ( 15 Junctions ) , 30% remaining delivery ( 35 junctions + 20 SVD + 20 ATCC and 10 TVD ) & commissioning, 25% Go Live. O & M : 5 Years CAPEX ~20.37 Cr & OPEX ~ 8.66 Cr | Phase-1 of 14 Junctions are Live – Payment collected (1039 L). Phase-2 – 16 Junctions completed & invoices submitted for payment. Phase-3 –10 Junctions and 44 Locations delivered & invoices submitted for payment. Received go ahead on 26-Aug-25 for 8 ITMS & 10 ATCS Junction (~4 Cr). Revised CAPEX now capped at 16Cr (+4 Cr) for work completion and payment processing. Reimbursement claims submitted for payment collection. O & M requested from 1st Sep 2024. Collection for due payments approx 500 L – Phase 2 and 3 along with electricity and connectivity reimbursement. | Go-Live expected by 13-Sep-25 & O&M maintenance activities. Due payment collection. Expected new order of 20 entry exit upgradation ANPR. | NA | 0 | 2025-08-29 | 20.23% | -20.41%
15 | IREL | West | Software Development | 1047.3631 | 162.9668 | 19 | 181.9668 | 115 | 884.3963 | 0 | 0 | SITC – 12 Months , O&M - 4 Yrs | 15.56% | Milestonewise | Start Date (PO) : 29-Oct-18 :: End Date (PO) : 30-Sep-25 | 23 | As per Achievement | Development of Integrated ERP System (IITS) (326 L) FMS including support & maintenance (147 L) Cloud Services (574 L) Change Request (63 K) | HRMS & Payroll – . 1] April Payroll Re-run for HO Employees - Due to the dump of production into the staging server, data and settings were impacted; Consequently, the April payroll needs to be re-run in preparation for the upcoming payroll demo scheduled next week. 1_a] Work is ongoing on creating pay contracts and updating employee data. 1_b] During the April payroll re-run, several issues were identified, including:. o EPF calculation mismatch for specific employees. o Incorrect pays lip calculations (certain allowances excluded). o Residual perks being calculated annually, whereas the amount is payable once in the next financial year. 1_c] These issues have been shared with the development team for corrections. Awaiting their updates before proceeding with the April payroll run. 2] Identified Issues & Coordination with Development Team – Post production dump into staging and the April payroll re-run, multiple issues were identified; Data updation has been initiated to support: 2_a] April payroll re-run. 2_b] Preparation of May payroll in staging. 2_c] Demo execution in production. Finance – . 1] Finance bugs fixing for the finance & payroll integration setup - completed | HRMS & Payroll – . 1] Completion of April Payroll Re-Run & May Payroll Demo - A trial run for the May payroll in IITS; The focus will be on completing the April payroll re-run and conducting the May payroll demo. 2] Ongoing Client Support and Coordination - Continue providing daily client support, resolving payroll-related queries, and assisting in optimizing payroll operations to improve process efficiency. MM -. 1] Add 2 Add 2 decimal in stock values for all transaction –Staging testing & production deployment. 2] Need to store pending status in all transaction except PO/WO –UAT testing & production deployment. 3] Cost Centre is not showing in SES accounting screen – QA testing & UAT testing. 4] Delete Items Provision in update mode in SES screen – QA testing & UAT testing. 5] Order type is blank in across all units – QA testing & UAT testing. Finance -. 1] Asset Management and Budgeting -modules in progress. 2] Data Migration - TB of units. 3] Payroll - Finance demo to the client. 4] Finance bugs fixing for the Chavara demo feedback. | Core Java, BIRD tool, postgre, ESDS cloud | 0 | 2025-08-29 |  | -955.1%
16 | Guwahati SC | East | Smart City | 669.1843 | 577.6653 | 0 | 577.6653 | 325 | 91.519 | 262.5109 | 0 | 1 Year + O&M | 86.32% | 10% of capex - Submission of Survey report, built report, project deployment plan. 50% - supply of material on pro-rata basis 15% - installation of material on pro-rata basis 15% - commissioning on pro-rata basis 5% - Go-live on pro-rata basis for individual system 5% - Overall Go-live of complete project. | Start Date (PO) : 10-Feb-25 :: End Date (PO) : 09-Feb-26 | 1 | As per Achievement | SITC for --. 1] 20 ECB. 2] 20 PA. 3] 10 ENV SENSOR. 4] 10 VMD. 5] 1 GIS Software. -- 5 years O&M after Go-live for supplied BOQ. | Site Survey done & report submitted to customer. GIS software invoicing done 315 L & installation completed - Configuration in process (SRS & FRS finalisation awaited). PA, ECB, EVS, EVS Poles (10 nos) materials delivered. EVS, PA-ECB, GIS, VMS software delivered. 1] Change request letter for VMD submitted by Honeywell to GSC -- approval received. 2] VMD Structure & Pole drawing approved by GSC. 3] EVS pole foundation 10/10 ready. | 1] EVS pole installtion after curing. 2] ECB encloser foundation & VMD Foundation work in progress 3] FRS & SRS for GIS software to submit -- In progress (under PMC review). 4] Collection of due payment. 5] FAT for VMD pole is scheduled from 28 to 29-Aug-25 & is in progress. | 0 | 0 | 2025-08-29 | 36.66% | 20%
17 | MCS - L&T | West | Smart City | 437.1641 | 361.0247 | 72 | 433.0247 | 171 | 76.1394 | 361.0247 | 72.5692 | 6 months | 82.58% | Monthly | Start Date (PO) : 01-Mar-25 :: End Date (PO) : 31-Aug-25 | 227 | 72.86 L | Viewing Manpower in 4 shifts including backup to cover 203 shifts daily. | Present work order is completed on 4th September,2025. However from customer side L&T Project Director Mr P R Kumar's mail stated 3 months extension. | 1) Raise invoice for August-2025 month with Supporting documents. 2) Recruitment for 20+ vacancies in project. | 0 | Although the customer mail received for extension but awaiting for actual work Order. | 2025-09-05 | 62.62%
18 | JNPA | West | EMS | 171.3136 | 0 | 0 | 0 | 0 | 171.3136 | 0 | 0 | 6 months + 5 Yr CAMC | 0% | Product Cost Payable on Product Delivery - 70% ICT Charges - 30% | Start Date (PO) : 07-Apr-25 :: End Date (PO) : 04-Oct-25 | 1 (shared) | 131.78 L | Design, Supply, Installation, Testing and Commissioning of web based enterprise energy and utility Management system with five years of Comprehensive Annual Maintenance Contract (CAMC) a) Complete built in energy monitoring system including power distribution monitoring of electrical & utility energy & consumption monitoring viz boundary level, process level and specific identified key areas. b) Demand management system that covers demand forecasting, scheduling and deviation monitoring w.r.t the schedule drawl c) Energy billing system that coverers consumer’s energy monitoring and billing #>Functional Requirements/ Deliverables : DATA ACQUISITION SYSTEM // DATA MANAGEMENT SYSTEM // DEMAND FORECASTING MODULE // Deviation Settlement Mechanism Module //Demand Management Module // Utility Billing Module – Electricity, Water & Rental #>Infrastructure Requirements: Server // Cloud Service (IaaS) // OS // DB // Networking | #Servers: Configured, tested, and delivered on 13-08-2025. #Substations (1,2,3): Communication network completed; IPs assigned. #ABT Meters: Two meters installed in custom panel, delivered on 13-08-2025; rack placed at permanent location. #Water Flow Meters: 62 delivered, 3 (40 mm) installed; balance pending location finalization. #RMU Communication: Survey completed; converter installation planned on 08-09-2025. #Billing Meter Communication: GPRS testing ongoing with live data at JNPA. | #Servers: Installation in NOC room on 08-09-2025. #Substations: Begin meter data retrieval post server installation. ABT Meters: Connect with incomer meters in coming week with electrical team. #Water Flow Meters: Awaiting JNPA’s approval for 25 mm & 40 mm meter scope. #RMU Communication: Converter installation & cabling for one RMU on 08-09-2025. #Billing Meters: Continue GPRS testing; VI SIM cards expected in 20–25 days. | 0 | #Water Flow Meters: Pending finalization of 400 mm & 100 mm locations, outage schedule from Water Dept., and clarification on 25 mm & 40 mm meter scope (mismatch in procured vs. required). #RMU Communication: JNPA’s network vendor unavailable; clarification needed on revised scope for fibre laying/splicing and switch availability. #Substations Integration: Availability of one port in the switch (rack installation by vendor Supertech) still pending. | 2025-09-08