## Data_summary
SN | Project | search_db | Project1 | Region | Type | Total PO Amt | Billed Till Date | Accrual | Total Revenue | Open AR | Open Billing | Billed YTD_FY25-26 | Current Month Billing | Project Duration | Billed | Billing Milestone | Project Dates | Resource | Milestone billing amount | Scope | Overall Progress | Weekly Plan | Technology / tools | Challenges / Risks | Update Date | Profit_YTD MIS | Profit_FY24-25_MIS | search_db1 | Project Manager / Lead
1 | INVEST INDIA | PMG INVEST INDIA | INVEST INDIA | North | Application Maintenance | 840.2445 | 610.7803 | 23 | 633.7803 | 55 | 229.4643 | 163.3809 | 23.3401 | 36 Months | 72.69% | Monthly | Start Date (PO) : 17-Jul-23 :: End Date (PO) : 16-Jul-26 | 15 | 23.34 L | Hiring of Professionals for -- Application Development and Maintenance – 36 months Front End and Back End developer – 8 Resources Full Stack developer, Solution Architect, QA Engineer, UI/UX designer, business analyst, QA automation tester, Project Manager – 1 resource each | S.no Bucket name No. of Tasks 1. No Status = 16 2. Estimation = 10 3. Designing = 4 4. To Do = 20 5. In Progress = 11 6. Under QA Testing = 8 7. User Acceptance Testing (UAT) = 6 8. Released on Production = 256 9. Closed = 119 | Task-5 need to deploy(last week not deployed) | NodeJS , HTML5/CSS , JS , React , Springboot Elastic, PostGreSQL , MySQL , MongoDB, Postman, API & SSO integration | Client has not the permission on AI task | 2025-10-08 | 54.85% | 43.23% | PMG INVEST INDIA | Amit K
2 | SBM-U | SWACHH BHARAT MISSION - SBM URBAN | SWACHH BHARAT MISSION - SBM | North | Application Maintenance | 1305.45 | 753.3242 | 36 | 789.3242 | 7 | 552.1258 | 253.8375 | 36.2625 | 36 Months | 57.71% | Monthly | Start Date (PO) : 10-Jan-24 :: End Date (PO) : 09-Jan-27 | 20 (7+13) | 36.26 L | Development, Maintenance and operations of an Integrated Portal for SBM used by the MoHUA Update and maintain the various modules and functionalities developed as a part of the “Integrated Swachhatam” portal update and maintain all mobile applications developed Resolve all the bugs, issues and queries raised for these developed functionalities | 20 resources on-boarded. (13 resources from GAIA – Tech Partner) Payment received till Aug’25. 2 resources onboarded for SS. Hiring ongoing for 3 resources from GAIA. DWR mobile app: changes ongoing for dumpsite. New SBM Dashboard ver2.0 (Legacy waste & Toilets): testing ongoing New SSJ page created for City pairing on website. UWM Action Plan: additional points added from CPEEHO: Dev done API written for Prayas, under testing. GFC-I1 Indicator logic understanding and automation ongoing. Engineer App: Geo location enabled in iOS/Android. Implementation of Media Service in Java-Ongoing. Bulk upload parser under implementation. Website updates ongoing. Migration of SBMurban.org domain from Cloud Flare to Cloud Front. | Maintenance activities: Daily ULB support, Website changes ongoing. New SBM Dashboard 2.0 development: legacy waste & Toilets: testing ongoing. DWR Mobile App pilot planned in Oct’25. Enable DWR for Dumpsite. SS Handover with IPSOS ongoing. Development setup & Code configuration is ongoing, Mobile App – Code Configuration ongoing | Angular, AWS Cloud, mySQl, Posgresql, NodeJS, Java, MongoDB, RESTAPI, HTML, PHP, MicroService, Quicksight,CSS, Flutter | 1. File approved from Ministry. Contract start date is 01 Oct, 2025. 2 resources onboarded from CMS. Need 3 developers (1 Angular + 1 NodeJS + 1 Power BI) from GAIA. 2. Majority of team members working remotely. 3. No WiFi at New location | 2025-10-01 | 20.4% | 19% | SWACHH BHARAT MISSION - SBM URBAN | Anoop K
3 | ORGI | orgi OFFICE OF REGISTRAR GENERAL OF INDIA - CRS | OFFICE OF REGISTRAR GENERAL OF INDIA - CRS | North | Application Maintenance | 849.8214 | 401.1039 | 67 | 468.1039 | 71 | 448.7175 | 147.5894 | 0 | 2 Years | 47.2% | Monthly | Start Date (PO) : 02-Apr-24 :: End Date (PO) : 01-Apr-26 | 26 | 35.2 L | Maintenance, operations & enhancement of ORGI CRS Web and Mobile Application(s) including migration of legacy data from State CRS applications to ORGI CRS and vice-versa through APIs. Resources for 2 years as below – Data Analytics, Database Administrator, Mobile App. Developer Android, Mobile App. Developer iOS, System Admin, Team Lead/Technical Project Manager, Training and Change Management Engineer, UI / Web Designer - 1 resource each. API Developers, Quality Assurance/ Test Engineer, Senior Application Developers – 2 resource each Application Developers, Technical Support (helpdesk) – 6 resource each | 1. 26 Resource deployed. 2. Development of new Module is under process as per CRS requirement. 3. DB , System performance and monitoring continue above 99.6 % availability. 4. State onboard is on going. 5. Receive Data from Non CRS State through API. 6. AADHAR , TRANSLITRATION and Payment Integrations. | 1. June Payment under process from FO . 2. July payment approval pending from RGI. 3. August document verification under processing. 4. Kalyan, Gaurang and Roopali Approval Pending from RGI 5. Aug Attendance approval under processing (Kalyan Roopli) 6 Sep Doc completed and Attendance not received 7. Payment Reconciliation Acknowledgement ,Old Death Digitization Report and Verification Screen, Deployment of GP Can extract Certificate, Application Flow Correction for Puducherry, 8. TN, Rajasthan and ORISSA DATA Mapping On Going 9. Integration of CRS Portal and UP MaNTrA | Node JS, Android, iOS, ORACLE database , REST, API design, HTML, CSS, JavaScript, JSON, IIS/ Apache, Linux, Aadhaar Vault, NSDL PayGov, C-DAC | 1. Family Care Tracker – Pilot Project (Integration of CRS BRN with Poshan Tracker, Techo+, and CTS Portals) 2 Indore IMC Zonal register creation 3. RU & Jurisdiction Mapping Phase 4: Functionality for Merging and Splitting of RU Units 4. SOP for the automation of the onboarding process of the states 5. Puducherry states will join CRS portal from 1st Nov with three regional Languages. 6. Approval for Kalyan, Gaurang, and Roopali is pending(Experience). August attendance will be verified after approval. | 2025-10-03 | 22.12% | 11.94% | orgi OFFICE OF REGISTRAR GENERAL OF INDIA - CRS | Dhananjay J
4 | ECCS NEW | EXPRESS CARGO CLEARANCE SYSTEM – ECCS NEW 2.0 | EXPRESS CARGO CLEARANCE SYSTEM – ECCS 2.0 | West | Application Maintenance | 2413.026 | 399.2692 | 273 | 672.2693 | 352 | 2013.7567 | 399.2692 | 0 | 2 years (incl. 3 month HOTO) | 16.55% | Quarterly | Start Date (PO) : 26-Sep-24 :: End Date (PO) : 25-Sep-26 | 68 | 287.27 L | Application Support, Onsite support Helpdesk Operations and Maintenance Services and upkeep of the ECCS Application Manage and deliver current and proposed CRs Deployment of Project Management software tools as per RFP Technological Upgradation of ECCS application The vendor is responsible for ECCS application technological upgrade. Application Upgrade Version Upgrade Architecture Upgrade User Interface Upgrade | Technology upgrade final presentation shared with estimation and manpower details to ADG. Few small changes deployment done on pre-prod & on production. 2 Task from Saddhit Target (E-mobility & Dwell Time In application) Demo has been given to WZU. July Attendance discussion is going on positively. | Taking all approvals for JAS. Payment from WZU for AMJ. Delivering Saddhit task on given date. SLA document last Meeting. Start Interviews for Full Stack Developer. | Java Struts, For upgrade - TBD | Productivity challenges observed among a few employees. Certain SLA parameters are challenging to achieve. Attendance marking on the CBIC portal for overlapping period of employee. RCA is in progress by WZU for full attendance marking on the CBIC portal by CMS for the past months.- Few verifications questions has given to study and answer. - July attendance approval raised by wzu. 3 positions needs to close. | 2025-10-03 | 37.26% | 33.03% | EXPRESS CARGO CLEARANCE SYSTEM – ECCS NEW 2.0 | Rahul S / Asmita S
5 | PFRDA | PENSION FUND REGULATORY AND DEVELOPMENT AUTHORITY - PFRDA | PENSION FUND REGULATORY AND DEVELOPMENT AUTHORITY - PFRDA | North | Software Development | 1265.6947 | 497.675 | 186 | 683.675 | 367 | 768.0197 | 62.2094 | 62.2094 | 1 yr Proj + 1 Yr Warr + 4 Yr AMC | 39.32% | 10% SRS ( 2m), 10% UAT( 7m), 10% VAPT/Audit ( 8m), 50% Implementation (9m), 10% training( 10m), 10% final Go-live ( 12m) for Solution cost of 622 L | Start Date (PO) : 18-Dec-23 :: End Date (PO) : 17-Dec-29 | 29 | As per achievment | Design, development, implementation and maintenance of PFRDA intranet portal(PINTRA) - internal digitalization (HRMS and finance) along with mobile app for HRMS Modules – HRMS, Finance, Admin, Legal, IT Management System 9 months Go-Live + 3 months Stabilisation + 1 Year Warranty + 4 Years AMC Payment Milestone : 10% SRS ( 2m), 10% UAT( 7m), 10% VAPT/Audit ( 8m), 50% Implementation (9m), 10% training( 10m), 10% final Go-live ( 12m) for Solution cost of 622 L Quarterly Payment for below; FMS during Warranty – 0.5 L / Qtr for 4 Qtr = 2 L MeitY empanelled GCC / VPC – 13.5 L/Qtr for 20 Qtr = 271 L Support Payment for Operations – 17.6 L/Qtr for 20 Qtr = 354 L CR – 17 L as & when required | → Bug fixes & service support (UAT Feedbacks resolved : Admin - 0 out of 41, Legal- 21 out of 25, IT-10 out of 19, HRMS-574 out of 585, F&A-39 out of 50). → Daily stand-up meetings started which includes PM; Also 7 key resource should seat at PFRDA for 1 month — requested by PFRDA as per meeting on 23rd July between CMS & PFRDA leadership - the same is in process. → VAPT done - certificate Received , → Payment collection for implementation milestone. | - HRMS Remain 11 point Fixing - Daily stand-up meetings started which includes PM; leadership - the same is in process. - Production issue Resolution - Payment collection for implementation milestone. - Finance Module Pending Points | Spring Boot, Odoo, React JS, Apache, PostgreSQL, Postman, Moodle, Figma, Ubuntu, AWS Cloud, Flutter, React, Node JS | 0 | 2025-09-29 |  |  | PENSION FUND REGULATORY AND DEVELOPMENT AUTHORITY - PFRDA | Dharmendra J
6 | DIC NHAI | DIGITAL INDIA CORPORATION - NATIONAL HIGHWAY AUTHORITY OF INDIA DIC NHAI | DIGITAL INDIA CORP - NATIONAL HIGHWAY AUTHORITY OF INDIA | North | Software Development | 2186.28 | 325.5 | 111 | 436.5 | 205 | 1860.78 | 325.5 | 0 | 3 Years | 14.89% | Track 1 (2m) - 10%, Track 2 (4m) – 20%, Track 3 (6m) – 20%, 8m – 50% | Start Date (PO) : 13-Nov-24 :: End Date (PO) : 12-Nov-27 | 38 | As per achievment, Phase 1 - 321 L | Developing and Maintaining a state-of-the-art Application to support transaction-based business processes covering entire lifecycle of National Highway projects of NHAI – Data Lake 2.0 upgradation. Payment Phase & milestone wise Track 1 (2m) - 10%, Track 2 (4m) – 20%, Track 3 (6m) – 20%, Track 4 (8m) – 50% Every phase of 6 months. Deployment of proposed 33 resources. (+5 in phase 2) | → Phase 1 all 4 tracks billing completed → Payment received till Track 3 for Phase 1. → All Nine modules of Phase I development done. → 7 in production 2 in UAT. → Drone moved to Phase II → Phase II requirement gathering done for BICRS, Road Closure, and Payments → Development in progress on BICRS module. | → Deployment of RSA, TM, BICRS and Team Structure on production. → Development of Road closure. → Requirement gather for other modules of phase II - CO Division (Onboarding, Toll Master), Schedule digitization (G, H & M), correspondence module, Document Library, Payment for AE. Employee Directory | No-SQL, Ruby, Python, Java, HTML, CSS, JavaScript, Angular, React, GIS/ML, Cloud - TBD, Node JS, Rest API | Phase ll timelines are tight given the volume of work and current resources. Timely onboarding of resources. | 2025-10-03 | 21.41% | 32.59% | DIGITAL INDIA CORPORATION - NATIONAL HIGHWAY AUTHORITY OF INDIA DIC NHAI | Mukul K / Agam V
7 | DAnFW | DEPARTMENT OF AGRICULTURE CORPORATION AND FARMER WELFARE DIVISION MINISTRY MAOFW DANFW DACFW dept of agri. | DEPT OF AGRICULTURE CORP & FARMER WELFARE | North | Application Maintenance | 1606.08 | 497.1459 | 68 | 565.1459 | 179 | 1108.9341 | 385.6203 | 0 | 2 Years | 30.95% | Monthly | Start Date (PO) : 05-Dec-24 :: End Date (PO) : 04-Dec-26 | 52+2 | 67.88 L | Deployment of technical resources for application development, customization and maintenance for ‘digital agriculture division, DA&FW’ Deployment of required 34 resources. 1 resource each – Team Lead, Sr Mobile Developer, tester, BA, content management expert. 2 resource each – Full stack/Sr Developer, UI/UX, API developer, mobile developer, dashboard expert, e-office support. 3 resource each – Sr Front end developer, VC support 5 resource – Full stack developer (>6 to <10 yrs.) 6 resource – Full stack developer (>3 to <6 yrs.) Deployment of 16 resources on need basis. | Krishi MApper • API Consumption 1. AMI API: reflecting on GIS/Survey Count dashboard 2. Mahadbt-API/patanjali API/karnatka RKVY API : WIP • Scheme on boarding 1. PKVY : feedback shared from tester - WIP for fixing issue 2. oil seed Assets : feedback shared from tester - WIP for fixing issue 3. NBM : testing on progress • Power BI Dashboard : Need to incorporate with API to get updated data • Count Dashboard— FY wise / scheme wise / state wise : testing going on over staging • GIS Dashboard : API/query optimization for data Natural Farming : • Fixing users highlighted issue AI-KOSH • APIs to share for metadata for all scheme : some APIs are shared : meeting schedule for review of API Krishi Unnati • MIS report discussed with client. Some design will shared to freeze before development start | Krishi MApper • API Consumption 1. Data count to show over dashoard for state API which is consumed 2. Mahadbt-API/patanjali API/karnatka RKVY API : consume and show over dashboard • Scheme on boarding 1. PKVY : deploy over production/play store 2. oil seed Assets : deploy over production/play store 3. NBM : deploy over production/play store • Power BI Dashboard : deploy over production • Count Dashboard— FY wise / scheme wise / state wise : deploy over production • GIS Dashboard :deploy over production Natural Farming : • Fixing users highlighted issue AI-KOSH • APIs to share for metadata for all scheme : all APIs to be share Krishi Unnati • MIS report : work on report | C#, ASP.NET, MVC, .NET Core, Visual Studio, HTML5, CSS3, RESTful API, MERN, flutter, react Native, MS SQL, e-Office | GIS dashboard/survey count query issue : query is more complex and need to optimize. A dedicated database developer is required at our end to fix it : one developer is already shortlisted and mailed for the further process | 2025-10-09 | 11% | 11% | DEPARTMENT OF AGRICULTURE CORPORATION AND FARMER WELFARE DIVISION MINISTRY MAOFW DANFW DACFW dept of agri. | Sourav M / Ravi R
8 | GWALIOR SC ICCC | GWALIOR SC ICCC | GWALIOR SC ICCC | West | Smart City | 1372.5806 | 430.5498 | 23 | 453.5498 | 244 | 942.0308 | 74.7324 | 0 | 62 month (incl. 2 mnth HOTO) | 31.37% | FMS – 11 L + Taxes (monthly billing) O&M – 13 L + Taxes (quarterly billing) Audit – 8 L + Taxes (yearly billing for 1st Year) Upgradation – 324 L + Taxes (60% - 194 L) | Start Date (PO) : 30-Aug-24 :: End Date (PO) : 31-Oct-29 | 32 | As per milestone | ICCC & DC upgradation with 5 years comprehensive AMC – 60% on SITC & 2% every Quarter with O&M payment CAMC of existing IT & non-IT infra - quarterly payment Manpower services: 39+1(non-billable) – monthly payment ICCC certifications – Yearly payment Provision – as & when required. | Q1 & Q2 payment and 60% Capex payment released. 32 Manpower deployed as per client requirements. Remaining Manpower deployment letter submitted to client for approval but client replied currently there is no requirement. ISO Certification Documents parts ready some parts are pending to client end for Audit. Q.3 O&M &Manpower and 2% of Capex. Payment file is at CEO for approval for final payment. Most probably before 15 oct payment will credit our accounts. AMC vendors payment not done on timely from CMS end. Switches, Servers and Tape Library HDD AMC Required. This is very critical our Dc. | Q.3 Payment file sign from CEO for final payment. Consumable ITem Diesel payment also released with o&m payment. Video wall and switches and NvR down due to natural lighting: assign to vendor and resolve this issues. For ISO 27001 when client is free some points cleared for Audit. Minimum wages latter submitted to client and discussed final approval. For DC infra AMC discussing to HO and purchase team. | NA | VENDORS PAYMENT NOT DONE TIMELY FROM CMS END. (Ramp display and CCSPL & SUDHIR SALES DG) AMC REQUIRED OLD DC INFRA ON URGENT BASIS. For ISO CERTIFICATION PUSH TO CLINT FROM OUR SALES TEAM. Video wall down last 8 days, Vendor PO pending. Insurance claim register for video wall and Switches. | 2025-10-09 | 19.54% | 11.44% | GWALIOR SC ICCC | Sachin S
9 | Kanpur SC O&M | Kanpur SC O&M tech mahindra TECHM | Kanpur SC O&M | North | Smart City | 5337.5 | 3431.25 | 762 | 4193.25 | 923 | 1906.25 | 762.5 | 0 | 42 month | 64.29% | Quarterly | Start Date (PO) : 01-Jan-23 :: End Date (PO) : 25-Jun-26 | 46 | 381 L | O&M support, AMC of all BOQ. Maintenance of Hardware, Network, Software, ICT Infrastructure, L1 , L2, L3 & OEM Support of all field solutions, DC & DR and applications for 42 months ( 50 junctions ) BG for 762 L to be submitted, advance payment of 2 Qtrs will be released after signing SOW. BG would be returned back to CMS after 4 Qtrs. PBG of 3% of balance of TCV (137 L) to be submitted at end of Qtr 4. | 1)Jan23 to Sept25 (Total 11 quarters payment released- 75%) 2)24 July meeting scheduled with commissioner to discuss issues related to ICCC critical issues & withhold payment- KSCL will not pay to TechM (re-imbursement)- KSCL will not pay to Tech M reimburesement and will have to be paid by Tech M to CMS 3) Billing done for OND24 & JFM24 Qtr | 1) To expedite ATCS -23 junctions for making it operational 2) VMSB issue resolution to keep it live 3) Reimbursement of recurring charges from Tech-M 4) Release of 25% retention/withheld amount 5) Coordination with vendor Videonetics for implementation of "Time for Red" as per the requirement of the client. 6) Coordination with vendor Text Local for redemption of credit points on vendor's migration to new portal 7)Follow-up on procurement of batteries, smart parking sensors, HDD for LPU's, | NA | 1) ATCS 23 junction activity work has suffered due to vendor M/s SPIT inactions in expediting works 2)Vendor Videonetics "Time for Red" feature not yet been delivered despite the forgone timeline. 3)Battery order is awaited 4)VMSB devices facing recurring problems (dark spots, black lines, component failures).Smart Parking sensors & VMSB card-related issues. 5)HDD order for LPU is awaited as a result of which system at various junction has downtime | 2025-10-09 | 25% | 51.23% | Kanpur SC O&M tech mahindra TECHM | Saleel H
10 | NMPT | NEW MANGALORE PORT TRUST - NMPT | NEW MANGALORE PORT TRUST - NMPT | South | CRP | 680.6929 | 225.4923 | 22 | 247.4923 | 33 | 455.2006 | 6.3876 | 0 | 5 years | 33.13% | Monthly | Start Date (PO) : 01-Jul-24 :: End Date (PO) : 01-Jul-29 | 15 | 7.3 L | Operation and Comprehensive annual Maintenance Contract (CAMC) of the RFID System for a Period of 5 years at NMPA. FMS – 12 data entry operators, 2 Technician, 1 Service Engineer Replacement of existing Infrastructure in 1st year. – 197 L (inc. KK & Cruise gate augmentation). Payment within 15 days after SITC of replacement. Integration with existing system. | 1. KK gate hardware installation is completed 2. Cruise gate hardware installation is completed. 3. Turnstile repair is pending PO need to be issued to vendor | Make sure of CAMC billing clearance of March April 2025 from NMPA end May June July 2025 bills should be submit to customer for clearance | NA | Turnstile repair | 2025-10-03 | -23.92% | 12.04% | NEW MANGALORE PORT TRUST - NMPT | Prashant P
11 | Vadodara Traffic | VADODARA VMC TRAFFIC | VADODARA VMC TRAFFIC | West | Smart City | 1045.7627 | 709.4025 | 0 | 709.4025 | 0 | 336.3602 | -0.5941 | 0 | SITC 4 Mths & O&M - 5 Yrs | 67.84% | After SITC | Start Date (PO) : 26-Feb-24 :: End Date (PO) : 25-Jun-29 | shared resource | full | Design, supply, Erection testing & commissioning of traffic signal at various 28 junction. Upgradation of old traffic signal at 44 Junction. Integration with existing system. 5 year comprehensive maintenance service. Payment 100% after successful installation. | Under O & M | O & M activity and once 302 light received we will start installation. | NA | 302 light under procurement we are already delay in material delivery and installation --- VMC ATCS 20 no CDT and 5 no of DC controller spare material procurement pending since long time.---VMC ATCS | 2025-10-03 |  | 18% | VADODARA VMC TRAFFIC | Sachin R
12 | VADODARA ICCC | VADODARA ICCC vadodara | VADODARA ICCC | West | Smart City | 2019.8763 | 331.9972 | 0 | 331.9972 | 0 | 1687.8792 | 171.1604 | 0 | 5 years | 16.44% | Quarterly | Start Date (PO) : 01-Aug-24 :: End Date (PO) : 31-Jul-29 | 17 | 100.99 L | O&M support, AMC of all BOQ. Maintenance of Hardware, Network, Software, ICT Infrastructure, L1 , L2, L3 & OEM Support of all field solutions, DC & DR and applications for 60 months Deployment of manpower : Project Manager (1), Technical Expert (4) [Network and Security, Video management, server-storage, CCC software], Electrician (4), Field staff (8) PBG of 3% | Maintenace activity | Q3 quarter invoice process. 6 no VMD module we will change 1 no 6 KVA ups received now we will live VMD | NA | VMD application testing done but controller replacement activity pending. New controller under procurement --- ICCC 05 no of VMD LED time have issue. Need to purchase new module - ICCC 22 no of UCON 10 controller we needs to replace. - ICCC 40 no location battery stolen. Insurance under process 16 no ups under repairing | 2025-10-09 | 21.71% | 20.46% | VADODARA ICCC vadodara | Sachin R
13 | ISCDL | INDORE SMART CITY ISCDL | INDORE SMART CITY | West | Smart City | 2903.0413 | 1722.0306 | 15 | 1737.0306 | 977 | 1181.0107 | 54.8212 | 0 | SITC – 9 M, O&M – 5 Yr | 59.32% | Quarterly | Start Date (PO) : 01-Nov-22 :: End Date (PO) : 31-Aug-29 | 6 | 43.3 L + Taxes (O&M) | Implementation of (ITMS) for 50 Junctions with Centralised Monitoring + 50 additional services Payment Milestone wise 5% Inception Report, 10% requirement Study, 30% material delivery & commissioning of 1 corridor ( 15 Junctions ) , 30% remaining delivery ( 35 junctions + 20 SVD + 20 ATCC and 10 TVD ) & commissioning, 25% Go Live. O & M : 5 Years CAPEX ~20.37 Cr & OPEX ~ 8.66 Cr | 1. Hold 11 ATCS and 9 ITMS junction work letter received. 2. Hold 3 TVDS, 3 SVDS, 19 PTZ location letter received. 3. Hold junction CAPEX cost approval and Billing mail received. 4. Today, Submitted invoices for completed work including other recurring cost are under signing by CEO sir, Verified by ISCDL team. As per ISCDL CEO Sir confirmation, partial payment of 50 Lakh will be released by upcoming week. | 1] New junction work of one no. 3 Arm ATCS-ITMS approval will be received from ISCDL in upcoming week. 2] As per CDO sir, Today Go-Live note sheet will prepare and will be released soon after the today billing note sheet signing by CEO sir. | NA | 1] Apart from 50Lakh payment, Rest all the recurring cost and capex cost will be released based on the availability of fund at smart city. 2. Work approval required from HO for the execution of ISCDL letter for 11 ATCS junction, 9 ITMS junctions, 3 TVDS and 3 SVDS. 2] Material approval including dispatching required as per site consumption report. | 2025-10-09 | -5.274% | -20.41% | INDORE SMART CITY ISCDL | Akash K
14 | IREL | INDIAN RARE EARTHS LIMITED - IREL | INDIAN RARE EARTHS LIMITED - IREL | West | Software Development | 1047.3631 | 162.9668 | 0 | 162.9668 | 115 | 884.3963 | 0 | 0 | SITC – 12 Months , O&M - 4 Yrs | 15.56% | Milestonewise | Start Date (PO) : 29-Oct-18 :: End Date (PO) : 30-Sep-25 | 21 | As per Achievement | Development of Integrated ERP System (IITS) (326 L) FMS including support & maintenance (147 L) Cloud Services (574 L) Change Request (63 K) | HRMS - Completed the feedback provided by Mr. Anil SM - Ship cum road way issue for IRN and Revert the PI qty and LC qty after short close FA - Running balance of GL for specific period shall have the opening balance row (separate) for income and expense. | Planning to complete buy back for MM, e-separation demo, SMS integration. | Core Java, BIRD tool, postgre, ESDS cloud | No risks involved | 2025-10-03 |  | -955.1% | INDIAN RARE EARTHS LIMITED - IREL | Priya R
15 | Guwahati SC | Guwahati SC Honeywell Automation India Limited | Guwahati SC | East | Smart City | 669.1843 | 650.5152 | 18 | 668.5152 | 411 | 18.6691 | 335.3608 | 0 | 1 Year + O&M | 97.21% | 10% of capex - Submission of Survey report, built report, project deployment plan. 50% - supply of material on pro-rata basis 15% - installation of material on pro-rata basis 15% - commissioning on pro-rata basis 5% - Go-live on pro-rata basis for individual system 5% - Overall Go-live of complete project. | Start Date (PO) : 10-Feb-25 :: End Date (PO) : 09-Feb-26 | 2 | As per Achievement | SITC for --. 1] 20 ECB. 2] 20 PA. 3] 10 ENV SENSOR. 4] 10 VMD. 5] 1 GIS Software. -- 5 years O&M after Go-live for supplied BOQ. | 1. EVS: 10/10 Nos. EVS Poles has been installed. EVS installation is pending due to Power and Network from Honeywell. 2. 6/10 Nos. VMD foundations done. 4 Nos. Pending due to digging work restricted by Client for Puja vacations up to 21st Oct'25, but we submitted an work permit letter for start the work from 6/10/25. Still not getting approval. 3. ECB, ECB enclosure, VMD Display board, VMD Poles, EVS, PA delivered at site and invoicing done. | 1. ECB enclosure foundation work. 2. EVS, ECB and PA cable laying work. | NA | 1. VMD controller still not delivered. 2. Accessories like Cat-6 cable, Earthing accessories, lightning arrestor, HDPE pipes make still not approved by client. Due this delivery pending. | 2025-10-02 | 36.66% | 20% | Guwahati SC Honeywell Automation India Limited | Arindam R
16 | MCS - L&T | Mumbai city surveillance larsen and toubro mcs | Mumbai City Surveillance | West | Smart City | 437.1641 | 433.0839 | 72 | 505.0839 | 188 | 4.0802 | 433.0839 | 0 | 6 months | 99.07% | Monthly | Start Date (PO) : 01-Mar-25 :: End Date (PO) : 31-Aug-25 | 218 | 72.86 L | Viewing Manpower in 4 shifts including backup to cover 203 shifts daily. | AR Collected till Jun-2025 i.e. 1.5Cr July-25 Invoice is Due 85L Aug-25 Invoice is Not Due 85L Pending Balance 1.8Cr | 1. Recruitment of 20 Operators 2. Workorder Follow-Up with Customer 3. Support Document preparation for upcoming Invoice | NA | 1. Recruitment according to Attrition - Multiple follow-up with Vendor for shortlisting and calling for recruitment. 2. New Work Order from Customer | 2025-10-09 | 61.44% |  | Mumbai city surveillance larsen and toubro mcs | Jaywant P
17 | JNPA | Jawaharlal Nehru Port Authority JNPA jnpt | Jawaharlal Nehru Port Authority | West | EMS | 171.3136 | 171.3136 | 0 | 171.3136 | 132 | 2.2034e-08 | 171.3136 | 39.5339 | 6 months + 5 Yr CAMC | 100% | Product Cost Payable on Product Delivery - 70% ICT Charges - 30% | Start Date (PO) : 07-Apr-25 :: End Date (PO) : 04-Oct-25 | 2 | 131.78 L | Design, Supply, Installation, Testing and Commissioning of web based enterprise energy and utility Management system with five years of Comprehensive Annual Maintenance Contract (CAMC) a) Complete built in energy monitoring system including power distribution monitoring of electrical & utility energy & consumption monitoring viz boundary level, process level and specific identified key areas. b) Demand management system that covers demand forecasting, scheduling and deviation monitoring w.r.t the schedule drawl c) Energy billing system that coverers consumer’s energy monitoring and billing ->>Functional Requirements/ Deliverables : DATA ACQUISITION SYSTEM // DATA MANAGEMENT SYSTEM // DEMAND FORECASTING MODULE // Deviation Settlement Mechanism Module //Demand Management Module // Utility Billing Module – Electricity, Water & Rental ->>Infrastructure Requirements: Server // Cloud Service (IaaS) // OS // DB // Networking | Core Infrastructure (Servers, Cloud, Panel Delivery): Completed Meter Communication (Substations & ABT): Partially completed, pending vendor/network readiness Water Meter Deployment: Materials delivered; ~30 units ready for installation once infra is provided Pending Dependencies: Switch rack/port enablement (CQTech), API from GE SCADA vendor, OFC & infra support from JNPA | one water meter installation as per infra ready from JNPA. ABT panel permanent placement besides main incomer panel. NDP pole installation for MPLS Link setup | PostgreSQL, DLMS, MODBUS, GPRS, Python, DotNet MVC | Dependency on third-party vendors (CQTech, GE SCADA) for switch ports & API availability. OFC network readiness at RMU locations pending from JNPA. Infra support delays (valves, strainers, ducts, power supply) affecting water meter installations. | 2025-10-08 |  |  | Jawaharlal Nehru Port Authority JNPA jnpt | Brayan F
18 | DIC ROB | DIGITAL INDIA CORP -PRD RAILWAY & ROB GIRDER INSPECTION PORTAL DIGITAL INDIA CORP -PRD RAILWAY & ROB GIRDER INSPECTION PORTAL DIC ROB | DIGITAL INDIA CORP - PRD RAILWAY & ROB GIRDER INSPECTION PORTAL | North | Software Development | 111.36 | 33.408 | 0 | 33.408 | 0 | 77.952 | 33.408 | 22.272 | 4 months + O&M | 30% | Track 1 - 10%, Track 2 – 20%, Track 3 – 20%, 8m – 50% | Start Date (PO) : 09-Jun-25 :: End Date (PO) : 08-Oct-25 | 12 | As per achievment. | Developing and Maintaining a state-of-the-art Application to used for handling the process related to constructing a railway girder over the roads/highways including various stages of requests, inspection and approval process involving different stakeholders/users. Need to automate & manage the process through web-based portal which is currently handled manually/paper-based. In Phase -1, The process related to Quality Assurance Plan (QAP) and Welding Procedure Specification Sheet (WPSS) will be automated. In Phase-2, rest of the processes to be automated. Payment Phase & milestone wise Track 1 - 10%, Track 2 – 20%, Track 3 – 20%, Track 4 – 50% Deployment of proposed resources for total 80 Man-months. | Modules Completed 1. Authentication Module – Implemented secure login and access control mechanism with proper user roles and permissions. 2. Landing Page – Developed and deployed interactive dashboard with quick navigation to all major modules. 3. Agency Selection – Functionality for selecting and managing agencies successfully integrated. 4. View Girder Assignment – Module to view girder assignment details completed and tested. 5. WPSS & QAP Submission Approver – Approval flow for WPSS and QAP submissions finalized and implemented. 6. Module Integration – All completed modules integrated seamlessly within the main application framework. 7. Inter-Service Communication – Microservice communication established through REST APIs for smooth data exchange. 8. View & Download GAD – Functionality to view and download GAD files successfully developed and tested. 9. Add New Girder & Contractor – Module for adding new girders and assigning contractors implemented. 10. Agency Selection (Extended) – Additional features and validations incorporated as per updated PRD. 11. GAD Management Module – Developed module for managing GAD-related data and documents. 12. Stakeholder & Employee Onboarding – Onboarding flow for stakeholders and employees completed, integrated with authentication service. 13. All core modules and approval workflows have been completed as per PRD. 14. API integration and inter-service communication successfully tested. 15. GAD Management and WPSS/QAP Approval flows are functional and aligned with updated requirements. 16. Stakeholder onboarding and agency management workflows are fully operational. 17.Email Integration – Successfully implemented and tested email service for notification and approval workflows. | 1. Girder Fabrication & Raw Material Approval Process – Partially completed; remaining integration and approval flow under development. 2. WPQR Preparation & Submission (Welding Procedure Qualification Record) – Partially completed; submission and approval components in progress. 3. Layout, Master Plates, Jigs, Joints & Fixtures – Inspection Request – Partially completed; inspection request generation and workflow integration ongoing. 4. Cutting, Straightening & Edge Preparation – Inspection Request – Partially completed; validation and backend service linkage under progress. Plan 1. Complete pending workflow integrations for fabrication and inspection modules. 2. Conduct testing of WPQR and inspection request flows. 3. Prepare modules for internal review and UAT. | JAVA 17, Springboot, PostgreSql, React, AWS Cloud, Microservices, NodeJS, Postman, Apache Tomcat webserver, SSL, Oauth, AWS ECS | 1. Due to continuous changes in PRD and Figma designs, development work is in progress. 2. The project comprises 302 screens (132 complex, 170 average), spanning Fabrication, Inspection, Workshop, and Approval modules. 3. Fabrication and Inspection modules exhibit high complexity owing to multiple process stages such as WPQR, Raw Material, Welding, and Assembly. 4.Approval workflows involving multi-level roles (Agency, ADE/B&S, Directors) add significant logic, validation, and access control complexity. | 2025-10-03 |  |  | DIGITAL INDIA CORP -PRD RAILWAY & ROB GIRDER INSPECTION PORTAL DIGITAL INDIA CORP -PRD RAILWAY & ROB GIRDER INSPECTION PORTAL DIC ROB | Dharmendra J
19 | DIC NOC | DIC NOC | DIGITAL INDIA CORP - NOC | North | Software Development | 218.28 | 0 | 0 | 0 | 0 | 218.28 | 0 | 0 | 0 | 0% | NA | Start Date (PO) : 03-Jul-25 :: End Date (PO) : Order to log | 12 | NA | Development, deployment, and support of NOC Portal with modules for Login, User Registration, Application Submission, and Approval workflows. Implementation of Registration & Validation including Mobile OTP, GST validation, Aadhaar integration, and User Authorization. Enable Application Submission with GIS data pickup, document upload, affidavit submission, e-sign, payment gateway, and Q&A module. Workflow automation for Right of Way (ROW) applications with end-to-end submission tracking. | Total 12 modules (functionalities) to be developed in this project. Completed - 5 In progress - 3 Pending (dependencies from Client) - 4 → Module-wise Status with remarks as below; ● Development Completed for: 1] CDAC E-Sign Integration - Fully integrated and tested. 2] Bharatkosh Payment Integration - Live and functional. 3] Amenity Listing - Finalized and ready for use. 4] Compliance Questions Validation Enhancement (Access) - Pending Review and approval. 5] Access Upload Drawings & Documents - Awaiting initiation and final approvals. ● Development In Progress for: 1] GIS Data Cleaning - Data refinement activities underway. 2] PA/CA/AE/IE User Data Cleaning - User data validation and cleaning ongoing. 3] GIS Data (Geo Server Setup) - Geo Server establishment blocked due to Docker image support issue; Shridhar is investigating. MoRTH confirmation is still awaited. ● Pending for: 1] UIDAI Aadhaar Integration - Awaiting initiation and final approvals. 2] Utility Listing - Awaiting initiation and final approvals 3] Compliance Questions Validation Enhancement (ROW) - Pending - Awaiting initiation and final approvals. 4] ROW Upload Drawings & Documents - Pending - Awaiting initiation and final approvals. | ● Expedite resolution of Geo Server/Docker issue. ● Obtain MoRTH confirmation for GIS data provisioning. ● Initiate UIDAI Aadhaar integration post prerequisites. | 0 | ● GIS Data / Geo Server: Docker image issue hindering setup; pending MoRTH confirmation. ● UIDAI Aadhaar Integration: Implementation to begin after receiving required approvals and environment setup. ● Template creation for Provisional License and Final License. | 2025-09-26 |  |  | DIC NOC | Pradeep N
20 | NeGD ITPO | NATIONAL E-GOVERNANCE DIV - ITPO BHARAT MANDAPAM NATIONAL E-GOVERNANCE DIV - ITPO BHARAT MANDAPAM NeGD ITPO | NATIONAL E-GOVERNANCE DIVISION - ITPO BHARAT MANDAPAM | North | Application Maintenance | 509.88 | 0 | 5 | 5 | 0 | 509.88 | 0 | 0 | 2 Years & extendable for 1 yr | 0% | Monthly | Start Date (PO) : 25-Aug-25 :: End Date (PO) : 24-Aug-27 | 4 | 21.25 L | Hiring of 14 Professionals to -- Handle the software project development, support & rollout services of DIC-NeGD projects. Primarily the services would range from core project development, implementation to management support in carrying out regular operational activities on a day-to-day basis – For 24 months extendable upto 1 Yr. Front End and Back End developer – 8 Resources (Including 1 senior developer each) Mobile App Developer – 2 resources Quality Analyst, DevOps, Project Manager cum Business Analyst, Data Entry Analyst (Platform Management) - 1 resource each | We are nearing the completion of the ITPO corporate website (main site static pages) development. This progress has been communicated to both ITPO and NeGD. We are working to fulfill the ITPO commitments made to the Ministry in August, prior to the deployment of the CMS team. | - Content and Images placement on webiste (if provided by concern person). - Development on the remaining pages - Meeting with ITPO and NeGD officials for Tally Integration | - Backend: Node.js (Java script- Nest.Js Framework) - Frontend: Angular - DB: MySQL | 0 | 2025-10-01 |  |  | NATIONAL E-GOVERNANCE DIV - ITPO BHARAT MANDAPAM NATIONAL E-GOVERNANCE DIV - ITPO BHARAT MANDAPAM NeGD ITPO | Raghavendra P
21 | MMRDA BTRS | MMRDA - BALASAHEB THAKRE RASHTRIYA SMARAK MMRDA - BALASAHEB THAKRE RASHTRIYA SMARAK MMRDA BTRS | MMRDA - BALASAHEB THAKRE RASHTRIYA SMARAK | West |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 months | 0% | 0 | Start Date (PO) : Yet to log Order :: End Date (PO) : . | NA | 0 L | EPC providing immersive experience in Gallery and Museum design with fit out and SITC of end-to-end solutions of technologies including existing systems, MEPF and O&M for 1 Year CMS Scope ( As Partner to EPC Contractor) SITC of BLE5 MESH NETWORK VISITOR MANGEMENT SITC of ICCC PLATFORM WITH LIDAR AND BI TOOLS SITC of VIDEO WALL & ASSOCIATED CONTROLLERS, CABLES & ACCESSORIES SITC of COMMAND & CONTROL ROOM INCLUDING CIVIL, INTERIORS, MEP SERVICES SITC of NETWORK, SECURITY MONITORING AND MANAGEMENT SITC of SERVERS , DESKTOPS AND ASSOCIATED INFRASTRUCTURE | We have still not received the order and SO is not generated, as per sales - Mr. Parag the final signature is awaited from customer side. | Once the Order is generated in our system we will ask Purchase to start taking the quotes and do negotiations along with Meeting with All identified vendors as per scope at site. | NA | Crisp delivery timeliness and multiple vendors to deliver the entire solution makes it complex and timely follow-up and push is needed. | 2025-09-25 |  |  | MMRDA - BALASAHEB THAKRE RASHTRIYA SMARAK MMRDA - BALASAHEB THAKRE RASHTRIYA SMARAK MMRDA BTRS | Vinod S