## Data_summary
SN | Project | Project1 | Region | Type | Total PO Amt | Billed Till Date | Accrual | Total Revenue | Open AR | Open Billing | Billed YTD_FY25-26 | Current Month Billing | Project Duration | Billed | Billing Milestone | Project Dates | Resource | Milestone billing amount | Scope | Overall Progress | Weekly Plan | Technology / tools | Challenges / Risks | Update Date | Profit_YTD MIS | Profit_FY24-25_MIS | search_db
1 | INVEST INDIA | INVEST INDIA | North | Application Maintenance | 840.2445 | 587.4402 | 23 | 610.4402 | 110 | 25280% | 140.0408 | 23.3401 | 36 Months | 0.69913 | Monthly | Start Date (PO) : 17-Jul-23 :: End Date (PO) : 16-Jul-26 | 15 | 23.34 L | Hiring of Professionals for -- Application Development and Maintenance – 36 months Front End and Back End developer – 8 Resources Full Stack developer, Solution Architect, QA Engineer, UI/UX designer, business analyst, QA automation tester, Project Manager – 1 resource each | -> Monthly billing from Jul-23 to Aug-25 done. -> Application maintenance and regular CR deployment. -> 356 tasks out of 413 tasks are in production as on date. -> Pragati meetings module is developed by CMS - These meetings are being chaired by Prime Minister of India. -> AWS Optimization has been done on all PMG environments as instructed by PMG team. -> Security Audit was done & agency has raised total 26 points, out of which 7 high priority tasks are completed & awaiting further action from Auditor. -> Customer wants AI module to be integrated, pitching our AI solution & will get additional order if selected. | Maintenance activities : -> Deployment of 2 task -- on UAT. -> 14 Tasks In progress (+ 9 Tasks in QA Testing, +3 in designing, +11 under estimation & + 15 Tasks in to do). -> Due payment collection (May to Aug 25). -> Replacement of Bimal Kalsa & Raghavendra Pratap on priority. | NodeJS , HTML5/CSS , JS , React , Springboot Elastic, PostGreSQL , MySQL , MongoDB, Postman, API & SSO integration | Replacement of Bimal Kalsa (Backend+Elastic Developer) - As per rfp terms we need to provide replacement with overlapping period of 30 days, if not then penalty equivalent to monthly amt of resource will be deducted. Replacement of Raghavendra Pratap on priority | 45911 | 0.58012 | 0.43234 | PMG INVEST INDIA
2 | SBM-U | SWACHH BHARAT MISSION - SBM | North | Application Maintenance | 1305.45 | 717.0617 | 36 | 753.0617 | 92 | 58839% | 217.575 | 36.2625 | 36 Months | 0.54928 | Monthly | Start Date (PO) : 10-Jan-24 :: End Date (PO) : 09-Jan-27 | 20 | 36.26 L | Development, Maintenance and operations of an Integrated Portal for SBM used by the MoHUA Update and maintain the various modules and functionalities developed as a part of the “Integrated Swachhatam” portal update and maintain all mobile applications developed Resolve all the bugs, issues and queries raised for these developed functionalities | 1] 20 resources on-boarded. (13 resources from GAIA – Tech Partner) 2] Payment received till May’25; Invoicing done for Aug’25. 3] 2 resources onboarded for SS. 1 will be joining today; Interviews ongoing for other 2 resources 4] DWR mobile app: changes ongoing for dumpsite. 5] New SBM Dashboard ver2'0 (Legacy waste & Toilets): Testing & Bug Fixing ongoing 6] New SBM Dashboard ver2'0 (UWM): Development ongoing 7] New SSJ page created for City pairing on website. 8] Dumpsite API modified for SHS portal. 9] Bulk upload parser under implementation 10] Website updates ongoing. 11] Discussion done with 3rd party security Auditor on portal and mobile app. | 1] Maintenance activities: Daily ULB support. 2] Website changes. 3] New SBM Dashboard 2'0 development: legacy waste & Toilets: Testing 4] New SBM Dashboard ver2'0 (UWM): Development 5] IHHL support ongoing. 6] Updates in SSJ page. 7] DWR Mobile App pilot to be planned; Enable DWR for Dumpsite. 8] SS Handover with IPSOS in the next week based on resource availability. | Angular, AWS Cloud, mySQl, Posgresql, NodeJS, Java, MongoDB, RESTAPI, HTML, PHP, MicroService, Quicksight,CSS, Flutter | 1] Need 2 developers (1 NodeJS + 1 Power BI) 2] Limited Seats available for team members in the ministry. 3] Majority of team members working remotely. 4] No Wi-Fi at New location | 45911 | 0.19 | 0.19 | SWACHH BHARAT MISSION - SBM URBAN
3 | ORGI | OFFICE OF REGISTRAR GENERAL OF INDIA - CRS | North | Application Maintenance | 849.8214 | 402.0658 | 67 | 469.0658 | 33 | 44776% | 148.5513 | 33.611 | 2 Years | 0.47312 | Monthly | Start Date (PO) : 02-Apr-24 :: End Date (PO) : 01-Apr-26 | 27 | 35.2 L | Maintenance, operations & enhancement of ORGI CRS Web and Mobile Application(s) including migration of legacy data from State CRS applications to ORGI CRS and vice-versa through APIs. Resources for 2 years as below – Data Analytics, Database Administrator, Mobile App. Developer Android, Mobile App. Developer iOS, System Admin, Team Lead/Technical Project Manager, Training and Change Management Engineer, UI / Web Designer - 1 resource each. API Developers, Quality Assurance/ Test Engineer, Senior Application Developers – 2 resource each Application Developers, Technical Support (helpdesk) – 6 resource each | # May 25 Bill Payment received. # June Payment under process. # Vikas July progress report verification is under progress. # July Draft invoice submitted -- approval pending. # New DB is deployed, 1 Tech support resource Joined. # GP Can extract Certificate # Gujarat Onboarding Successfully done on 01-Sep-2025. # Commitee formed for current contract extension. | # Indore IMC Zonal register creation. # Pondicherry state to join CRS portal. # WSO2 to NAPIX Shifting. # Gujarat onboarding from 15-Aug-25. # Contract extension approval -- proposal submitted. | Node JS, Android, iOS, ORACLE database , REST, API design, HTML, CSS, JavaScript, JSON, IIS/ Apache, Linux, Aadhaar Vault, NSDL PayGov, C-DAC | WSO2 server issues. | 45905 | 0.22607 | 0.11942 | orgi OFFICE OF REGISTRAR GENERAL OF INDIA - CRS
4 | ECCS NEW | EXPRESS CARGO CLEARANCE SYSTEM – ECCS 2.0 | West | Application Maintenance | 2413.026 | 399.2692 | 182 | 581.2693 | 471 | 201376% | 399.2692 | 0 | 2 years (incl. 3 month HOTO) | 0.16546 | Quarterly | Start Date (PO) : 26-Sep-24 :: End Date (PO) : 25-Sep-26 | 68 | 287.27 L | Application Support, Onsite support Helpdesk Operations and Maintenance Services and upkeep of the ECCS Application Manage and deliver current and proposed CRs Deployment of Project Management software tools as per RFP Technological Upgradation of ECCS application The vendor is responsible for ECCS application technological upgrade. Application Upgrade Version Upgrade Architecture Upgrade User Interface Upgrade | All critical resources have been onboarded. All AMJ quarter data has been sent to the client for releasing 80% payment. Successfully delivering the weekly dwell time report – an ad-hoc requirement apart from CR/in-application work. New technology upgrade planning is in progress. Received 80% payment for FM. | Finalizing the new technology upgrade. Finalizing the SLA document (except 3 pending points). Closing all approvals for AMJ (for 20% payment). Initiated approvals for July. Payment release discussion for Tatwa with Avdhoot. | Java Struts, For upgrade - TBD | From WZU, we require the SOP and process changes for each approval, as WZU has recently revised the approval procedure. Productivity challenges observed among a few employees. Certain SLA parameters are challenging to achieve. Attendance marking on the CBIC portal for absent employees. RCA is in progress by WZU for full attendance marking on the CBIC portal by CMS for the past months. | 45911 | 0.41621 | 0.33027 | EXPRESS CARGO CLEARANCE SYSTEM – ECCS NEW 2.0
5 | PFRDA | PENSION FUND REGULATORY AND DEVELOPMENT AUTHORITY - PFRDA | North | Software Development | 1265.6947 | 435.4656 | 0 | 435.4656 | 367 | 83023% | 0 | 0 | 1 yr Proj + 1 Yr Warr + 4 Yr AMC | 0.34405 | 10% SRS ( 2m), 10% UAT( 7m), 10% VAPT/Audit ( 8m), 50% Implementation (9m), 10% training( 10m), 10% final Go-live ( 12m) for Solution cost of 622 L | Start Date (PO) : 18-Dec-23 :: End Date (PO) : 17-Dec-29 | 26 | As per achievment | Design, development, implementation and maintenance of PFRDA intranet portal(PINTRA) - internal digitalization (HRMS and finance) along with mobile app for HRMS Modules – HRMS, Finance, Admin, Legal, IT Management System 9 months Go-Live + 3 months Stabilisation + 1 Year Warranty + 4 Years AMC Payment Milestone : 10% SRS ( 2m), 10% UAT( 7m), 10% VAPT/Audit ( 8m), 50% Implementation (9m), 10% training( 10m), 10% final Go-live ( 12m) for Solution cost of 622 L Quarterly Payment for below; FMS during Warranty – 0.5 L / Qtr for 4 Qtr = 2 L MeitY empanelled GCC / VPC – 13.5 L/Qtr for 20 Qtr = 271 L Support Payment for Operations – 17.6 L/Qtr for 20 Qtr = 354 L CR – 17 L as & when required | # System study / SRS/ FRS; UAT & implementation for payment milestones completed -- Same is billed & payment collected for SRS & UAT milestone. # Go-Live done on 19th May 2025. # Helpdesk set-up done. # Mobile App (1) –Complete. iOS app will be shared after dev account is received. | # Bug fixes & service support (UAT Feedbacks resolved : Admin - 0 out of 41, Legal- 21 out of 25, IT-10 out of 19, HRMS-529 out of 585, F&A-35 out of 50). # Daily stand-up meetings started which includes PM; Also 7 key resource should seat at PFRDA for 1 month -- requested by PFRDA as per meeting on 23rd July between CMS & PFRDA leadership - the same is in process. # VAPT to be done - VAPT environment created & shared with AKS IT for further process. # Payment collection for implementation milestone. # Billing for remaining milestones. | Spring Boot, Odoo, React JS, Apache, PostgreSQL, Postman, Moodle, Figma, Ubuntu, AWS Cloud, Flutter, React, Node JS | 0% | 45897 |  |  | PENSION FUND REGULATORY AND DEVELOPMENT AUTHORITY - PFRDA
6 | DIC NHAI | DIGITAL INDIA CORP - NATIONAL HIGHWAY AUTHORITY OF INDIA | North | Software Development | 2186.28 | 325.5 | 245 | 570.5 | 77 | 186078% | 325.5 | 162.75 | 3 Years | 0.14888 | Track 1 (2m) - 10%, Track 2 (4m) – 20%, Track 3 (6m) – 20%, 8m – 50% | Start Date (PO) : 13-Nov-24 :: End Date (PO) : 12-Nov-27 | 38+4 | As per achievment, Phase 1 - 321 L | Developing and Maintaining a state-of-the-art Application to support transaction-based business processes covering entire lifecycle of National Highway projects of NHAI – Data Lake 2.0 upgradation. Payment Phase & milestone wise Track 1 (2m) - 10%, Track 2 (4m) – 20%, Track 3 (6m) – 20%, Track 4 (8m) – 50% Every phase of 6 months. Deployment of proposed 33 resources. (+5 in phase 2) | # DIC team along with CMS team working on this project. # Total 9 modules in part 1 & Total 8 modules in part 2 including Drone module (moved from part 1 to part 2). # 9 out of 9 – development complete & UAT done for part 1. # Go-live of 7 completed modules done on 17th Jul 2025 -- awaiting official sign-off. | # Production deployment of remaining 2 modules - Road Safety Audit & toilet Maintenance. # Next Part-2 modules decision -- requirement analysis in progress for 7 modules; yet to start for employee directory & drone module. # Post Go-live activities -- SOP creation of helpdesk support, user manual etc. | No-SQL, Ruby, Python, Java, HTML, CSS, JavaScript, Angular, React, GIS/ML, Cloud - TBD, Node JS, Rest API | 0% | 45897 | 0.27641 | 0.32591 | DIGITAL INDIA CORPORATION - NATIONAL HIGHWAY AUTHORITY OF INDIA DIC NHAI
7 | DAnFW | DEPT OF AGRICULTURE CORP & FARMER WELFARE | North | Application Maintenance | 1606.08 | 497.1459 | 68 | 565.1459 | 99 | 110893% | 385.6203 | 67.878 | 2 Years | 0.30954 | Monthly | Start Date (PO) : 05-Dec-24 :: End Date (PO) : 04-Dec-26 | 52+2 | 67.88 L | Deployment of technical resources for application development, customization and maintenance for ‘digital agriculture division, DA&FW’ Deployment of required 34 resources. 1 resource each – Team Lead, Sr Mobile Developer, tester, BA, content management expert. 2 resource each – Full stack/Sr Developer, UI/UX, API developer, mobile developer, dashboard expert, e-office support. 3 resource each – Sr Front end developer, VC support 5 resource – Full stack developer (>6 to <10 yrs.) 6 resource – Full stack developer (>3 to <6 yrs.) Deployment of 16 resources on need basis. | 35 resources onboarded out of 35, including 1 additional Team Lead approval from customer. 15 resources onboarded out of 15 – additional on need basis approval received from customer. 2 VC Support addnl order received -- onboarded. 1 Drupal & 1 SEO developer onboarded on temporary basis (FOC basis) Billing till Jul-25 done. Payment of 136 L received on 26-Aug-2025 (till Jun-25) 1] KM (Krishi Mapper) – #Applying Scheduler on Telangana State API for NMEO-OP #New API applied on 12 schemes on GIS #Optimizing current GIS Dashboard #GIS – Cluster has been applied till District level #KM Dashboard new layout is in progress #Aligned meeting with Maha DBT team for API discussion 2] Natural Farming - Fixing users highlighted issue. 3] MIDH-APP – Added 8 new components in mobile app online mode and deployed on play store (Under Review) - Working on Offline mode. 4] Krishi Unnati – Mother/Daily sanction module: In Progress | 1] NFSM – Make Agristack data live on Krishi Mapper 2] KM – #GIS google map with optimized API will push on Live #PDMC data will push on Live #Discussion on new UM layout #Preparing Model flow or GT scheme #UM – Optimizing the counts records #Onboard consumed API’s data on KM #Fixing UM bugs 3] NF – #Work on Given Observation points #Providing Data Import option | C#, ASP.NET, MVC, .NET Core, Visual Studio, HTML5, CSS3, RESTful API, MERN, flutter, react Native, MS SQL, e-Office | 0% | 45904 | 0.11 | 0.11 | DEPARTMENT OF AGRICULTURE CORPORATION AND FARMER WELFARE DIVISION MINISTRY MAOFW DANFW DACFW dept of agri.
8 | GWALIOR SC ICCC | GWALIOR SC ICCC | West | Smart City | 1372.5806 | 430.5498 | 46 | 476.5498 | 204 | 94203% | 74.7324 | 33.4494 | 62 month (incl. 2 mnth HOTO) | 0.31368 | FMS – 11 L + Taxes (monthly billing) O&M – 13 L + Taxes (quarterly billing) Audit – 8 L + Taxes (yearly billing for 1st Year) Upgradation – 324 L + Taxes (60% - 194 L) | Start Date (PO) : 30-Aug-24 :: End Date (PO) : 31-Oct-29 | 32 | As per milestone | ICCC & DC upgradation with 5 years comprehensive AMC – 60% on SITC & 2% every Quarter with O&M payment CAMC of existing IT & non-IT infra - quarterly payment Manpower services: 39+1(non-billable) – monthly payment ICCC certifications – Yearly payment Provision – as & when required. | -> UI/UX developer joining in progress client approval pending. -> 3rd Qtr Invoice and all details submit to PDMC for SLA calculation. -> Server, Storage &Tape library HDD AMC Required -- Pending from Vendor and purchase team. -> WLD Display installation pending from Siemens Vendor. -> ISO 27001 Documents work in progress. | -> Payment file move from consultant to Client for note sheet and approval. -> Follow up for approval to UI/UX developer joining -> Follow up for WLD display and server storage to our purchase team. | NA | from Purchase team finalize server and storage AMC ASAP. | 45912 | 0.1954 | 0.11442 | GWALIOR SC ICCC
9 | Kanpur SC O&M | Kanpur SC O&M | North | Smart City | 5337.5 | 3431.25 | 635 | 4066.25 | 916 | 190625% | 762.5 | 0 | 42 month | 0.64286 | Quarterly | Start Date (PO) : 01-Jan-23 :: End Date (PO) : 25-Jun-26 | 31 + 2 + 14(TP) | 381 L | O&M support, AMC of all BOQ. Maintenance of Hardware, Network, Software, ICT Infrastructure, L1 , L2, L3 & OEM Support of all field solutions, DC & DR and applications for 42 months ( 50 junctions ) BG for 762 L to be submitted, advance payment of 2 Qtrs will be released after signing SOW. BG would be returned back to CMS after 4 Qtrs. PBG of 3% of balance of TCV (137 L) to be submitted at end of Qtr 4. | Jan 23 to Mar 25 (Total 9 quarters payment released-75%). 24 July meeting scheduled with commissioner to discuss issues related to ICCC critical issues & withold payment -- KSCL will not pay to TechM (re-imbursement) & has to be paid by TechM to CMS. Billing done for OND24 & JFM25 Qtr. Neat-Park application demonstration to client is carried out on 23rd Oct 2024; Client has suggested few points, Team has incorporated the same - Payment integration is in progress (Bank details awaited from client - will share after VAPT) -- VAPT completed & feedback points also closed on 28-Aug-25. EMS OEM onboarding done - OEM Team repairing work in progress. Collected ~ 632 L till JFM-25. | Smart Parking- Payment integration is in progress (bank details awaited) -- VAPT done & feedback points closed on 28-Aug-25. Reimbursement of recurring charges from TechM. Release of 25% retention/withheld amount -- In progress. | NA | Delay in release of withheld amount (25%), recurring charges reimbursement. | 45897 | 0.25 | 0.5123 | Kanpur SC O&M tech mahindra TECHM
10 | NMPT | NEW MANGALORE PORT TRUST - NMPT | South | CRP | 680.6929 | 239.8516 | 22 | 261.8516 | 50 | 44084% | 20.7468 | 0 | 5 years | 0.35236 | Monthly | Start Date (PO) : 01-Jul-24 :: End Date (PO) : 01-Jul-29 | 15 | 7.3 L | Operation and Comprehensive annual Maintenance Contract (CAMC) of the RFID System for a Period of 5 years at NMPA. FMS – 12 data entry operators, 2 Technician, 1 Service Engineer Replacement of existing Infrastructure in 1st year. – 197 L (inc. KK & Cruise gate augmentation). Payment within 15 days after SITC of replacement. Integration with existing system. | Support Started from 1st July 2024. Installation is complete for FRS & UHF system for main gate. Received WO for kk & cruise gate on 3rd Oct 24, to be completed in 3 months (03-Jan-2024) -- Taken exclusion as both Gates not ready from NMPT. KK Gate - 2 lanes system installed on temporary basis; Cabling provision is done for installation at both KK & cruise gate. CAMC Billing done till May-25. | Regular maintenance activities. Support activities for UHF Reader, HF Reader, and FRS applications; Official Go-live expected but payment for the milestone is received from NMPT (177 L ~ on 22-Aug-25). Payment collection for Apr-25 to May-25 CAMC invoices. | NA | 0% | 45898 | -0.25968 | 0.12041 | NEW MANGALORE PORT TRUST - NMPT
11 | Vadodara Traffic | VADODARA VMC TRAFFIC | West | Smart City | 1045.7627 | 709.4025 | 0 | 709.4025 | 0 | 33636% | -0.5941 | 0 | SITC 4 Mths & O&M - 5 Yrs | 0.67836 | After SITC | Start Date (PO) : 26-Feb-24 :: End Date (PO) : 25-Jun-29 | sharing resources | full | Design, supply, Erection testing & commissioning of traffic signal at various 28 junction. Upgradation of old traffic signal at 44 Junction. Integration with existing system. 5 year comprehensive maintenance service. Payment 100% after successful installation. | 90 | 302 traffic light material delivery and installation. | NA | 302 traffic light delivery | 45915 |  | 0.18 | VADODARA VMC TRAFFIC
12 | VADODARA ICCC | VADODARA ICCC | West | Smart City | 2019.8763 | 331.9972 | 0 | 331.9972 | 0 | 168788% | 171.1604 | 0 | 5 years | 0.16437 | Quarterly | Start Date (PO) : 01-Aug-24 :: End Date (PO) : 31-Jul-29 | 7 +10(shared) / 17 | 100.99 L | O&M support, AMC of all BOQ. Maintenance of Hardware, Network, Software, ICT Infrastructure, L1 , L2, L3 & OEM Support of all field solutions, DC & DR and applications for 60 months Deployment of manpower : Project Manager (1), Technical Expert (4) [Network and Security, Video management, server-storage, CCC software], Electrician (4), Field staff (8) PBG of 3% | Contract agreement signed . PBG of 3 % submitted All resources has onboarded. BOM and other detail shared with purchase team for finalization of contract. First Qtr payment received ~ 80 L on 28-May-25 Third quarter invoice submitted. | Start maintenance activity as per SLA Third quarter invoice submitted. Payment collection. (2nd & 3rd Qtr) | NA | 0% | 45898 | 0.2049 | 0.20464 | VADODARA ICCC vadodara
13 | ISCDL | INDORE SMART CITY | West | Smart City | 2903.0413 | 1722.0306 | 0 | 1722.0306 | 977 | 118101% | 54.8212 | 0 | SITC – 9 M, O&M – 5 Yr | 0.59318 | Quarterly | Start Date (PO) : 01-Nov-22 :: End Date (PO) : 31-Aug-29 | 6 | 43.3 L + Taxes (O&M) | Implementation of (ITMS) for 50 Junctions with Centralised Monitoring + 50 additional services Payment Milestone wise 5% Inception Report, 10% requirement Study, 30% material delivery & commissioning of 1 corridor ( 15 Junctions ) , 30% remaining delivery ( 35 junctions + 20 SVD + 20 ATCC and 10 TVD ) & commissioning, 25% Go Live. O & M : 5 Years CAPEX ~20.37 Cr & OPEX ~ 8.66 Cr | 1] Hold 11 ATCS and 9 ITMS junction work letter received from ISCDL for complete the work. 2] Hold 3 TVDS, 3 SVDS, 19 PTZ location work letter received from ISCDL for complete the work. 3] Submitted invoices for completed work including other recurring cost are verified and under signing process by ISCDL team. 4] CAPEX cost of 2.43CR note sheet are ready for CEO sign and approval. | 1] On Monday dt: - 15-09-2025, CEO sir will join the office, Post CDO sir will submit the note sheet for CEO sir sign and approval. 2] Hold junction CAPEX cost approval submitted at ISCDL and briefed to CDO sir for CEO sir approval. 3] With the discussion with CEO sir, CDO Sir will release the GO-Live letter. | NA | 1] Work approval required from HO for the execution of ISCDL letter for 11 ATCS junctions, 9 ITMS junctions, 3 SVDS, 3 TVDS and 19 PTZs. 2] Material approval including dispatching required as per site consumption report. 3] Still no clarity received from Smart city regarding the availability of Payment receipt from different resources. | 45910 | 0.20227 | -0.20414 | INDORE SMART CITY ISCDL
14 | IREL | INDIAN RARE EARTHS LIMITED - IREL | West | Software Development | 1047.3631 | 162.9668 | 0 | 162.9668 | 115 | 88440% | 0 | 0 | SITC – 12 Months , O&M - 4 Yrs | 0.1556 | Milestonewise | Start Date (PO) : 29-Oct-18 :: End Date (PO) : 30-Sep-25 | 23 | As per Achievement | Development of Integrated ERP System (IITS) (326 L) FMS including support & maintenance (147 L) Cloud Services (574 L) Change Request (63 K) | -> HRMS- Payroll : Ongoing Tasks a] Post Demo Activities - Shared identified points with the development team for enhancements, including: o Loan module improvements: interest calculation, handling cases where no EMI is deducted, impact on other loans, and loan recovery planning (Actual vs Draft Recovery Plan). o Payroll integration with reimbursement payment processing. o Integration of Earned Leave (EL) with initial pay computation. o Income tax computation updates, including perquisite calculation with a screen-view option for detailed visibility. b] Reports – Attendance - Visited and discussed with IREL HO HR team regarding attendance calculation process and logic. o Conducted comparison between IREL’s calculation and our system-generated report: o Identified use of sandwich rule for leave calculation. o Consideration of tour status as present. o Verified physical attendance against report data. o Highlighted a discrepancy in IREL’s May attendance data for one employee (incorrect record). o Discussed issues related to missing attendance updates for retired employees on their last day. o Raised ticket and assigned to developer for necessary corrections. -> Finance: 1] Production and Feedback bugs fixing 2] Functional Support to developers and cross-functional teams 3] Cashflow movement to production server 4] Segment reports moved to production server -> MM : 1] Add 2 decimal in stock values for all transaction – Completed, Deploy on Production server 2] Last transaction date update in Chavara unit – Completed, Deploy on Production server 3] Cancel Provision in Purchase order and Work order transaction - Development in Process 4] Order type is blank in across all units – Chavara and MK is in Process 5] ITC blank in Purchase Requisition – OSCOM & MK is in Process 6] Transactional Non-moving material code incorporates in SIV transaction – QA & UAT testing 7] Production issues -5, Resolved. | -> HRMS - Payroll : a] Testing & Validation - o Test all changes suggested during demo. o Execute payroll runs for April, May, and June with updated logic. b] Ongoing Client Support & Coordination o Continue addressing daily payroll-related queries. o Provide support for payroll operations. o Assist clients in streamlining payroll processes to improve efficiency. -> Finance : 1] Production and Feedback bugs fixing 2] Validation with actual data for cashflow statement 3] Validation with actual data for segment reports -> MM : 1] Last transaction date update in RED unit – Update on Production server 2] Cancel Provision in Purchase order and Work order transaction - UAT & Production deployment 3] Order type is blank in across all units – Chavara and MK will complete 4] ITC blank in Purchase Requisition – OSCOM & MK will complete 5] Transactional Non-moving material code incorporates in SIV transaction – UAT & Production deployment | Core Java, BIRD tool, postgre, ESDS cloud | 1] Payment release 2] Unstable ERP behavior for computation | 45911 |  | -9.551 | INDIAN RARE EARTHS LIMITED - IREL
15 | Guwahati SC | Guwahati SC | East | Smart City | 669.1843 | 577.6653 | 0 | 577.6653 | 325 | 9152% | 262.5109 | 0 | 1 Year + O&M | 0.86324 | 10% of capex - Submission of Survey report, built report, project deployment plan. 50% - supply of material on pro-rata basis 15% - installation of material on pro-rata basis 15% - commissioning on pro-rata basis 5% - Go-live on pro-rata basis for individual system 5% - Overall Go-live of complete project. | Start Date (PO) : 10-Feb-25 :: End Date (PO) : 09-Feb-26 | 1 | As per Achievement | SITC for --. 1] 20 ECB. 2] 20 PA. 3] 10 ENV SENSOR. 4] 10 VMD. 5] 1 GIS Software. -- 5 years O&M after Go-live for supplied BOQ. | Site Survey done & report submitted to customer. GIS software invoicing done 315 L & installation completed - Configuration in process (SRS & FRS finalization awaited). PA, ECB, EVS, EVS Poles (10 nos) materials delivered. EVS, PA-ECB, GIS, VMS software delivered. 1] Change request letter for VMD submitted by Honeywell to GSC -- approval received. 2] VMD Structure & Pole drawing approved by GSC. 3] EVS pole foundation 10/10 ready. | 1] EVS pole installation after curing. 2] ECB encloser foundation & VMD Foundation work in progress 3] FRS & SRS for GIS software to submit -- In progress (under PMC review). 4] Collection of due payment. 5] FAT for VMD pole is scheduled from 28 to 29-Aug-25 & is in progress. | 0% | 0% | 45898 | 0.36662 | 0.2 | Guwahati SC Honeywell Automation India Limited
16 | MCS - L&T | Mumbai City Surveillance | West | Smart City | 437.1641 | 433.0839 | 73 | 506.0839 | 257 | 408% | 433.0839 | 72.0592 | 6 months | 0.99067 | Monthly | Start Date (PO) : 01-Mar-25 :: End Date (PO) : 31-Aug-25 | 226 | 72.86 L | Viewing Manpower in 4 shifts including backup to cover 203 shifts daily. | Present work order is completed on 4th September,2025. However from customer side L&T Project Director Mr P R Kumar's mail stated 3 months extension. | 1) Raise invoice for August-2025 month with Supporting documents. 2) Recruitment for 20+ vacancies in project | 0% | Although the customer mail received for extension but awaiting for actual work Order. | 45905 | 0.62625 |  | Mumbai city surveillance larsen and toubro mcs
17 | JNPA | Jawaharlal Nehru Port Authority | West | EMS | 171.3136 | 0 | 0 | 0 | 0 | 17131% | 0 | 0 | 6 months + 5 Yr CAMC | 0 | Product Cost Payable on Product Delivery - 70% ICT Charges - 30% | Start Date (PO) : 07-Apr-25 :: End Date (PO) : 04-Oct-25 | 2 | 131.78 L | Design, Supply, Installation, Testing and Commissioning of web based enterprise energy and utility Management system with five years of Comprehensive Annual Maintenance Contract (CAMC) a) Complete built in energy monitoring system including power distribution monitoring of electrical & utility energy & consumption monitoring viz boundary level, process level and specific identified key areas. b) Demand management system that covers demand forecasting, scheduling and deviation monitoring w.r.t the schedule drawl c) Energy billing system that coverers consumer’s energy monitoring and billing #>Functional Requirements/ Deliverables : DATA ACQUISITION SYSTEM // DATA MANAGEMENT SYSTEM // DEMAND FORECASTING MODULE // Deviation Settlement Mechanism Module //Demand Management Module // Utility Billing Module – Electricity, Water & Rental #>Infrastructure Requirements: Server // Cloud Service (IaaS) // OS // DB // Networking | #Servers: Configured, tested, and delivered on 13-08-2025. #Substations (1,2,3): Communication network completed; IPs assigned. #ABT Meters: Two meters installed in custom panel, delivered on 13-08-2025; rack placed at permanent location. #Water Flow Meters: 62 delivered, 3 (40 mm) installed; balance pending location finalization. #RMU Communication: Survey completed; converter installation planned on 08-09-2025. #Billing Meter Communication: GPRS testing ongoing with live data at JNPA. | #Servers: Installation in NOC room on 08-09-2025. #Substations: Begin meter data retrieval post server installation. ABT Meters: Connect with incomer meters in coming week with electrical team. #Water Flow Meters: Awaiting JNPA’s approval for 25 mm & 40 mm meter scope. #RMU Communication: Converter installation & cabling for one RMU on 08-09-2025. #Billing Meters: Continue GPRS testing; VI SIM cards expected in 20–25 days. | 0% | #Water Flow Meters: Pending finalization of 400 mm & 100 mm locations, outage schedule from Water Dept., and clarification on 25 mm & 40 mm meter scope (mismatch in procured vs. required). #RMU Communication: JNPA’s network vendor unavailable; clarification needed on revised scope for fibre laying/splicing and switch availability. #Substations Integration: Availability of one port in the switch (rack installation by vendor Supertech) still pending. | 45905 |  |  | Jawaharlal Nehru Port Authority JNPA jnpt
18 | DIC ROB | DIGITAL INDIA CORP - PRD RAILWAY & ROB GIRDER INSPECTION PORTAL | North | Software Development | 111.36 | 0 | 0 | 0 | 0 | 11136% | 0 | 0 | 4 months + O&M | 0 | Track 1 - 10%, Track 2 – 20%, Track 3 – 20%, 8m – 50% | Start Date (PO) : 09-Jun-25 :: End Date (PO) : 08-Oct-25 | 12 | As per achievment. | Developing and Maintaining a state-of-the-art Application to used for handling the process related to constructing a railway girder over the roads/highways including various stages of requests, inspection and approval process involving different stakeholders/users. Need to automate & manage the process through web-based portal which is currently handled manually/paper-based. In Phase -1, The process related to Quality Assurance Plan (QAP) and Welding Procedure Specification Sheet (WPSS) will be automated. In Phase-2, rest of the processes to be automated. Payment Phase & milestone wise Track 1 - 10%, Track 2 – 20%, Track 3 – 20%, Track 4 – 50% Deployment of proposed resources for total 80 Man-months. | As per work order, we need to develop complete ROB portal (both Phase-1 and Phase-2) and make it live in 4 months -- by 8th Oct25. The tentative end date for the Project is 31st Oct 25 (from CMS). The Phase 1 (MVP) for ROB Project has gone live on 21st July 2025; Phase 2 in progress. A total of 46/80 Man Months has been consumed till 5th Sept 25 in the Project. | Billing for ROB to be done in 3rd week of September. | 0% | 0% | 45909 |  |  | DIGITAL INDIA CORP -PRD RAILWAY & ROB GIRDER INSPECTION PORTAL DIGITAL INDIA CORP -PRD RAILWAY & ROB GIRDER INSPECTION PORTAL DIC ROB
19 | DIC NOC | DIGITAL INDIA CORP - NOC | North | Software Development | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | NA | Start Date (PO) : 03-Jul-25 :: End Date (PO) : 00-Jan-00 | 11 | NA | Development, deployment, and support of NOC Portal with modules for Login, User Registration, Application Submission, and Approval workflows. Implementation of Registration & Validation including Mobile OTP, GST validation, Aadhaar integration, and User Authorization. Enable Application Submission with GIS data pickup, document upload, affidavit submission, e-sign, payment gateway, and Q&A module. Workflow automation for Right of Way (ROW) applications with end-to-end submission tracking. | 11 resources are deployed on this project. Development is completed from our side -- Data is awaited from Morth & NHAI to test the Application -- Expected by Sept 3rd week. A total of 21 Man Months has been consumed till 5th Sept 25 in the Project. | Application testing after Data is received. Work Order / LOI to be received. | 0% | Work Order / LOI to be received. | 45910 |  |  | DIC NOC
20 | NeGD ITPO | NATIONAL E-GOVERNANCE DIVISION - ITPO BHARAT MANDAPAM | North | Application Maintenance | 509.88 | 0 | 0 | 0 | 0 | 50988% | 0 | 0 | 2 Years & extendable for 1 yr | 0 | Monthly | Start Date (PO) : 25-Aug-25 :: End Date (PO) : 24-Aug-27 | 4 | 21.25 L | Hiring of 14 Professionals to -- Handle the software project development, support & rollout services of DIC-NeGD projects. Primarily the services would range from core project development, implementation to management support in carrying out regular operational activities on a day-to-day basis – For 24 months extendable upto 1 Yr. Front End and Back End developer – 8 Resources (Including 1 senior developer each) Mobile App Developer – 2 resources Quality Analyst, DevOps, Project Manager cum Business Analyst, Data Entry Analyst (Platform Management) - 1 resource each | Kick-off meeting done with customer. PBG, escalation matrix, signed work order copy submitted to customer. Resources identified from other projects & same will be onboarded after concurrence from customer. | Onboarding of resources as per requirement. | 0% | Stringent timeline to deploy resources - 21 days. Failure to Deploy Resources -- If less than 70% of selected resources join within 1 week of the Work Order : The bidder may be debarred and blacklisted for 3 years. | 45910 |  |  | NATIONAL E-GOVERNANCE DIV - ITPO BHARAT MANDAPAM NATIONAL E-GOVERNANCE DIV - ITPO BHARAT MANDAPAM NeGD ITPO
21 | MMRDA BTRS | MMRDA - BALASAHEB THAKRE RASHTRIYA SMARAK | West |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 18 months | 0 | 0 | Start Date (PO) : 00-Jan-00 :: End Date (PO) : 00-Jan-00 | 0 | 0 L | EPC providing immersive experience in Gallery and Museum design with fit out and SITC of end-to-end solutions of technologies including existing systems, MEPF and O&M for 1 Year CMS Scope ( As Partner to EPC Contractor) SITC of BLE5 MESH NETWORK VISITOR MANGEMENT SITC of ICCC PLATFORM WITH LIDAR AND BI TOOLS SITC of VIDEO WALL & ASSOCIATED CONTROLLERS, CABLES & ACCESSORIES SITC of COMMAND & CONTROL ROOM INCLUDING CIVIL, INTERIORS, MEP SERVICES SITC of NETWORK, SECURITY MONITORING AND MANAGEMENT SITC of SERVERS , DESKTOPS AND ASSOCIATED INFRASTRUCTURE | LOI is expected from MSI Pre-TAT activities done Project initiation activities under progress BOQ is being finalized Discussion with OEM to be initiated post receiving of LOI | Discussion with OEM to be initiated post receiving of LOI | 0% | 0% | 45910 |  |  | MMRDA - BALASAHEB THAKRE RASHTRIYA SMARAK MMRDA - BALASAHEB THAKRE RASHTRIYA SMARAK MMRDA BTRS